## Berth Planner
TPL-BERTH-01
Dock / Berth Occupancy Planner
Free PM Templates & Documents for Shipyard Newbuild Projects · Interactive — edit Start Date or Duration and the occupancy bar moves, so double-bookings show up immediately
Shipyard |  | [ Enter yard name ]
Planning Period Start (editable — shifts the whole planner) |  | 2026-01-05
Planning Horizon |  | 52 weeks (1 year)
Vessel / Hull No. | Owner | Purpose | Duration (days) | Start Date | End Date | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52
Dry Dock 1
Hull 214 – "Atlas OPV" | Harbour Patrol Authority | New Construction | 210 | 2026-01-05 |  | In Progress
Hull 215 – "Meridian Star" | Meridian Shipping Co. | New Construction | 308 | 2026-12-07 |  | Planned
Dry Dock 2
MV Bosphorus Star | Aegean Lines | Repair | 21 | 2026-01-19 |  | Completed
MV Kaptan Ahmet | Marmara Shipping | Repair | 14 | 2026-03-16 |  | Completed
Hull 216 – "Horizon II" | Coastal Defense Agency | New Construction | 280 | 2026-05-25 |  | Planned
Outfitting Quay A
Hull 213 – "Pioneer" | Blue Wave Ferries | Outfitting | 140 | 2026-01-05 |  | In Progress
Hull 214 – "Atlas OPV" | Harbour Patrol Authority | Outfitting | 126 | 2026-08-03 |  | Planned
Outfitting Quay B
MV Golden Bosphorus | Owner Layup / Storage | Layup | 364 | 2026-01-05 |  | Ongoing
Repair Berth
MV Nordic Trader | Nordic Shipping | Repair | 14 | 2026-02-09 |  | Completed
MV Anatolia | Anatolia Lines | Repair | 14 | 2026-04-20 |  | Completed
MV Levant | Levant Maritime | Repair | 14 | 2026-07-20 |  | Planned
MV Star Fisher | Star Fisheries | Repair | 7 | 2026-10-12 |  | Planned
Legend: ■ New Construction ■ Repair ■ Outfitting ■ Layup · Live: edit Start Date or Duration on any row and the occupancy bar moves — overlaps become visible immediately
This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.
Downloaded from https://project2-me.com/dokumanlar · © Project2-me