## Read me
TPL-SPM-T1 ¦ project2-me.com
Yacht Project Parameter Sheet (T1)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From the Superyacht Project Management lesson track on project2-me.com.
What it is for
One page that fixes the parameters every later plan depends on: size, tonnage target, use, rules, flag, class, price basis, programme and scope.
Every value carries its basis (a source or the reason for the choice), who decides it and by when.
How to use it
1. Start on the Blank sheet. The parameter names are pre-filled; add or delete rows to suit your project.
2. Status: Decided (signed off), Assumed (working value, needs confirmation), Open (no value yet).
3. Review the sheet at each design loop and before contract. An Assumed or Open line after contract is a risk item.
4. Keep the Needed by column honest: it is the latest point a decision can wait without moving the schedule.
About the example sheet
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
The contract price is shown as an index (100). No currency figure is given.
Ranges quoted in the Basis column come from public sources listed in the lesson; they are not design guidance for a real yacht.

## Blank
TPL-SPM-T1 ¦ project2-me.com
Yacht Project Parameter Sheet
Project: ____________ Revision: ____ Date: ________
Ref | Group | Parameter | Value | Basis / source | Decision owner | Needed by | Status | Notes
P01 | Identity | Working name
P02 | Identity | Yacht type and build model
P03 | Design | Length overall (LOA)
P04 | Rules | Gross tonnage target
P05 | Rules | Intended use
P06 | Rules | Guest capacity
P07 | Rules | Code
P08 | Rules | Flag
P09 | Rules | Class society and notation
P10 | Design | Hull and superstructure material
P11 | Design | Crew number
P12 | Commercial | Contract price
P13 | Commercial | Stage payments
P14 | Programme | Contract to delivery
P15 | Programme | Interior outfitting duration
P16 | Delivery and aftercare | Warranty period
P17 | Delivery and aftercare | Sea trial content
P18 | Scope | Tenders
P19 | Scope | Support vessel

## Example (YP-48, illustrative)
TPL-SPM-T1 ¦ project2-me.com
Yacht Project Parameter Sheet: Project YP-48 (fictional)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Ref | Group | Parameter | Value | Basis / source | Decision owner | Needed by | Status | Notes
P01 | Identity | Working name | Project YP-48 (code name) | Code name so the example cannot be confused with a real yacht | Owner | Before tender | Decided | Final name is the Owner's choice
P02 | Identity | Yacht type and build model | Motor yacht, full custom | Semi-custom was the alternative considered | Owner | Before tender | Decided
P03 | Design | Length overall (LOA) | 48 m | Boat International (Mar 2026): most sub-500 GT yachts are around 45 m; about 55 m reported as the practical ceiling | Owner, Design Studio | Before tender | Decided
P04 | Rules | Gross tonnage target | Below 500 GT (design target 499 GT) | Boat International: SOLAS equipment, ISPS and ISM obligations apply above 500 GT | Owner | Before tender | Decided | Track GT at every design loop
P05 | Rules | Intended use | Private and charter (commercial use) | Commercial use brings a 24 m+ yacht under REG Yacht Code Part A | Owner | Before tender | Decided
P06 | Rules | Guest capacity | 12 | Part A limit is 12 passengers; 13 or more moves to Part B | Owner | Before tender | Decided
P07 | Rules | Code | REG Yacht Code, Part A, July 2024 edition | Red Ensign Group | Owner's rep | Before tender | Decided
P08 | Rules | Flag | A Red Ensign Category 1 register (to be selected) | REG: Category 1 registers take ships of unlimited tonnage and type | Owner | Before contract | Open
P09 | Rules | Class society and notation | An IACS class society (to be selected) | Notation text to be copied from the chosen rule book, never paraphrased | Owner, Yard | Before contract | Open
P10 | Design | Hull and superstructure material | Steel hull, aluminium superstructure | Assumption for the example, not sourced | Design Studio, Yard | Before contract | Assumed | To be confirmed
P11 | Design | Crew number |  | No source; set with the captain and the flag's manning rules | Owner, Captain | Design freeze | Open
P12 | Commercial | Contract price | Index 100 | Budget shown as an index; no currency figure in this example | Owner | Contract | Decided | All other costs expressed against this index
P13 | Commercial | Stage payments | 7, including signing | Boat International: six to eight stage payments are typical | Owner, Yard | Contract | Decided | Percentages set in Lesson 6
P14 | Programme | Contract to delivery | 30 months | Industry guides give 24 to 48+ months for superyachts; Boat International gives one to five years | Owner, Yard | Contract | Decided | Illustrative choice within the range
P15 | Programme | Interior outfitting duration | About 12 months | Boat International: outfitting takes 6 to 18 months | Yard | Contract | Assumed
P16 | Delivery and aftercare | Warranty period | 12 months from delivery | Boat International: warranty checks within the first 12 months | Owner, Yard | Contract | Decided | Equipment warranties may differ
P17 | Delivery and aftercare | Sea trial content | Harbour tests, speed, endurance, manoeuvring, anchoring, tender launch, noise and vibration | Yard and surveyor guidance on yacht sea trials | Owner's rep, Yard | Design freeze | Assumed | Duration and location open
P18 | Scope | Tenders | 1 limousine tender, 1 RIB | RCD 2013/53/EU covers craft of 2.5 to 24 m | Owner | Design freeze | Open | Tender lengths open
P19 | Scope | Support vessel | Optional, separate project | Decision deferred | Owner | Month 6 | Open