## Read Me
TPL-SPM-T8 ¦ project2-me.com
Yacht Master Schedule Template (T8)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From project2-me.com, lesson: The Master Schedule for a Yacht Build.
What is in this file
Blank: an empty schedule with the same columns and a month-by-month bar chart (months 0 to 30 from contract).
Example (YP-48, illustrative): the 30-month master schedule used in the lesson, 8 WBS groups, 32 rows.
How to use it
Type Duration and Start (month). Finish is calculated. Bars and milestone diamonds redraw automatically.
Type is one of: Summary, Activity, Milestone. Critical = Yes paints the bar orange.
Excel does not recalculate dates from the Predecessors column. That column is a record of the logic.
For a schedule that recalculates, open the companion file yp-48-yacht-master-schedule-ms-project.xml
in Microsoft Project (File > Open, file type XML Format). It is MS Project XML, not an .mpp file.
Predecessor notation follows MS Project: 4SS+2 mo means start 2 months after task 4 starts.
About the example
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Durations sit inside publicly reported ranges (build 24 to 48 months or longer; outfitting 6 to 18 months).
Equipment lead times, the paint window length and trial duration are illustrative, not sourced. Replace them with your own.
The contract value is not shown. Payment milestones are marked but no percentages are given.

## Blank
TPL-SPM-T8 ¦ project2-me.com
Yacht Master Schedule
Months from contract signature (month 0). Replace with your own project.
ID | WBS | Task name | Type | Duration (months) | Predecessors | Start (month) | Finish (month) | Total float (months) | Critical | Payment milestone | Notes | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30

## Example (YP-48, illustrative)
TPL-SPM-T8 ¦ project2-me.com
YP-48 Master Schedule (illustrative)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
ID | WBS | Task name | Type | Duration (months) | Predecessors | Start (month) | Finish (month) | Total float (months) | Critical | Payment milestone | Notes | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | 1 | Contract and project milestones | Summary | 0 |  | 0
2 | 1.1 | Contract signature | Milestone | 0 |  | 0 |  | 0 | Yes | Yes
3 | 2 | Design and engineering | Summary | 14 |  | 0
4 | 2.1 | Basic design and class/flag plan approval | Activity | 7 | 2 | 0 |  | 0 | Yes |  | Class and flag not selected in the example.
5 | 2.2 | Design freeze (GA and interior layout) | Milestone | 0 | 4 | 7 |  | 2 | No
6 | 2.3 | Detail and production engineering | Activity | 12 | 4SS+2 mo | 2 |  | 0 | Yes
7 | 2.4 | Interior detail design and sample approval | Activity | 11 | 4SS+3 mo | 3 |  | 1 | No
8 | 3 | Long-lead procurement | Summary | 19 |  | 1
9 | 3.1 | Propulsion package: order to delivery | Activity | 11 | 2FS+1 mo | 1 |  | 1 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
10 | 3.2 | Generator sets: order to delivery | Activity | 11 | 2FS+2 mo | 2 |  | 1 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
11 | 3.3 | Stabilizers: order to delivery | Activity | 11 | 2FS+2 mo | 2 |  | 1 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
12 | 3.4 | Glazing and exterior doors: order to delivery | Activity | 9 | 5 | 7 |  | 9 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
13 | 3.5 | Interior joinery package: award and prefabrication | Activity | 7 | 5 | 7 |  | 2 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
14 | 3.6 | AV/IT and navigation: order to delivery | Activity | 6 | 7 | 14 |  | 1 | No |  | Lead time illustrative, not sourced: replace with maker's quoted slot and delivery.
15 | 4 | Hull and superstructure | Summary | 12 |  | 4
16 | 4.1 | Start of steel cutting | Milestone | 0 | 6SS+2 mo | 4 |  | 0 | Yes
17 | 4.2 | Steel hull construction (built inverted, turned) | Activity | 7 | 16 | 4 |  | 0 | Yes
18 | 4.3 | Keel laying | Milestone | 0 | 17SS+1 mo | 5 |  | 25 | No | Yes
19 | 4.4 | Aluminium superstructure construction | Activity | 7 | 17SS+4 mo | 8 |  | 0 | Yes |  | Steel hull with aluminium superstructure assumed for the example.
20 | 4.5 | Join superstructure to hull | Activity | 1 | 17, 19 | 15 |  | 0 | Yes
21 | 4.6 | Hull and superstructure joined | Milestone | 0 | 20 | 16 |  | 0 | Yes | Yes
22 | 5 | Systems installation | Summary | 11 |  | 12
23 | 5.1 | Main engine and gearbox installation and alignment | Activity | 2 | 9, 17 | 12 |  | 1 | No
24 | 5.2 | Main engines installed and aligned | Milestone | 0 | 23 | 14 |  | 16 | No | Yes
25 | 5.3 | Generator and stabilizer installation | Activity | 2 | 10, 11 | 13 |  | 1 | No
26 | 5.4 | Piping, HVAC, electrical and cabling | Activity | 11 | 23SS | 12 |  | 1 | No
27 | 5.5 | Hot work complete | Milestone | 0 | 21, 25 | 16 |  | 0 | Yes
28 | 6 | Fairing, paint and exterior | Summary | 10 |  | 16
29 | 6.1 | Fairing and exterior paint | Activity | 8 | 27 | 16 |  | 0 | Yes |  | Paint window length illustrative, not sourced.
30 | 6.2 | Exterior outfitting: glazing, teak, rails | Activity | 2 | 29, 12 | 24 |  | 1 | No
31 | 7 | Interior and AV/IT | Summary | 12 |  | 15
32 | 7.1 | Interior outfitting | Activity | 12 | 7, 13, 26SS+3 mo | 15 |  | 1 | No
33 | 7.2 | AV/IT installation | Activity | 3 | 14, 32SS+5 mo | 20 |  | 1 | No
34 | 8 | Commissioning, trials and delivery | Summary | 6 |  | 24
35 | 8.1 | Launch | Milestone | 0 | 29, 26 | 24 |  | 0 | Yes | Yes
36 | 8.2 | Commissioning and harbour acceptance tests | Activity | 3 | 35, 33 | 24 |  | 0 | Yes
37 | 8.3 | Sea trials | Activity | 1 | 36, 30 | 27 |  | 0 | Yes |  | Trial duration illustrative, not sourced.
38 | 8.4 | Sea trials complete | Milestone | 0 | 37 | 28 |  | 0 | Yes | Yes
39 | 8.5 | Punch list close-out, final finish, crew handover | Activity | 2 | 38, 32 | 28 |  | 0 | Yes
40 | 8.6 | Delivery | Milestone | 0 | 39 | 30 |  | 0 | Yes | Yes
Legend: orange bar = critical (total float 0), blue bar = has float, navy bar = WBS summary, ◆ = milestone.