## Read me
TPL-SPM-T2 ¦ project2-me.com
Yacht Build RACI Matrix (T2)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From Lesson 2 of the Superyacht Project Management track on project2-me.com: Who Does What on a Yacht Build.
What it is for
One matrix that says, for each key activity of a yacht newbuild, who does the work, who answers for the outcome, who is consulted before the decision and who is told afterwards. A second table sets how far the owner's representative may decide without going back to the Owner.
The letters
R Responsible: does the work.
A Accountable: answers for the outcome and signs it off. Exactly one A per row.
C Consulted: gives input before the decision (two-way).
I Informed: is told after the decision (one-way).
A/R The same party does the work and answers for it (e.g. the Yard's own schedule).
For approval rows the A sits with the body whose signature closes the item (class, flag). The Yard's contractual duty to obtain the approval stays in the contract, not in the matrix.
How to use it
1. Fix the columns first. If your naval architect works for the Owner, or two studios share the design, rename or add columns.
2. Work through each row with the Owner's side. The One-A check column flags any row without exactly one A.
3. Fill the delegated authority table and issue it as a letter from the Owner, copied to the Yard.
4. Agree both at the kick-off meeting with the Yard present and keep them under revision control.
5. Pair it with a communication matrix (who reports what, how often, which channel); the RACI does not replace it.
About the example sheet
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
In YP-48 the Owner contracts the Yard, the Design Studio and the owner's representative; the naval architect is engaged by the Yard; the build captain is employed by the Owner; the broker's role ends at contract signature. Class is an IACS class society and the flag a Red Ensign Category 1 register, neither yet chosen.
Authority limits are illustrative and shown as index points against a contract price of 100. They are not industry norms.

## Blank
TPL-SPM-T2 ¦ project2-me.com
Yacht Build RACI Matrix
Project: ____________ Revision: ____ Date: ________
Responsibility matrix (R = does the work, A = accountable, C = consulted, I = informed, A/R = both)
Ref | Phase | Activity | Owner | Owner's rep | Build captain | Design Studio | Naval architect | Yard | Class | Flag | One-A check | Notes
R01 | Pre-contract | Design brief and intended use (charter, guests, cruising area)
R02 | Pre-contract | Choice of code, flag and class society
R03 | Pre-contract | Yard selection and contract negotiation
R04 | Design and engineering | Exterior styling and general arrangement
R05 | Design and engineering | Hull form, stability, weight and GT budget
R06 | Design and engineering | Class plan approval (hull and machinery)
R07 | Design and engineering | Code plan approval for items the flag keeps
R08 | Design and engineering | Interior design, samples and mock-ups
R09 | Construction | Owner change request: scope, price and time
R10 | Construction | Master schedule and progress reporting
R11 | Construction | Milestone completion and payment release
R12 | Construction | Owner-furnished equipment supply
R13 | Construction | Workmanship inspections and punch list
R14 | Trials and delivery | Harbour acceptance tests and sea trials
R15 | Trials and delivery | Crew recruitment, manning and safety management
R16 | Trials and delivery | Acceptance and protocol of delivery
R17 | Trials and delivery | Registration and statutory certificates
R18 | Warranty | Warranty claims in the first year
Delegated authority of the owner's representative
Ref | Decision |  | Owner's rep may decide |  |  | Goes to the Owner | [5 empty] | Notes
D01 | Owner change request, price effect
D02 | Owner change request, delivery date effect
D03 | Change affecting GT budget, class notation or exterior profile
D04 | Drawing comments within the approved specification
D05 | Interior samples and finishes
D06 | Milestone completion certificate
D07 | Acceptance at delivery
D08
D09
D10
D11
Project: ____________ Revision: ____ Issued by: ____________ Date: ________ Agreed at kick-off by: Owner / Owner's rep / Yard

## Example (YP-48, illustrative)
TPL-SPM-T2 ¦ project2-me.com
Yacht Build RACI Matrix: Project YP-48 (fictional)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Responsibility matrix (R = does the work, A = accountable, C = consulted, I = informed, A/R = both)
Ref | Phase | Activity | Owner | Owner's rep | Build captain | Design Studio | Naval architect | Yard | Class | Flag | One-A check | Notes
R01 | Pre-contract | Design brief and intended use (charter, guests, cruising area) | A | R | C | C | C |  |  |  |  | Sets the code, the GT target and the guest count
R02 | Pre-contract | Choice of code, flag and class society | A | R | C | I | C | C |  |  |  | Lesson 3 covers the consequences
R03 | Pre-contract | Yard selection and contract negotiation | A | R | C | C | [5 empty] | Broker and counsel support this row; they are not matrix columns
R04 | Design and engineering | Exterior styling and general arrangement | A | C | C | R | C | C |  |  |  | Naval architect checks every GA change for weight, stability and GT
R05 | Design and engineering | Hull form, stability, weight and GT budget | I | C |  | C | R | A | C | C |  | In YP-48 the naval architect is engaged by the Yard
R06 | Design and engineering | Class plan approval (hull and machinery) |  | I |  |  | R | R | A | I |  | A = the body whose sign-off closes the item
R07 | Design and engineering | Code plan approval for items the flag keeps |  | I |  |  | R | R | C | A |  | Split between flag and RO to be confirmed with the chosen register
R08 | Design and engineering | Interior design, samples and mock-ups | A | C | C | R | C | C |  |  |  | Naval architect consulted on weight of stone and joinery
R09 | Construction | Owner change request: scope, price and time | A | R | C | C | C | C | I | I |  | Yard prices it; Owner's rep may approve within the delegated limit
R10 | Construction | Master schedule and progress reporting | I | C | I | I |  | A/R |  |  |  | Owner's rep reviews, does not own the yard's schedule
R11 | Construction | Milestone completion and payment release | A | R | C |  |  | R | C |  |  | Yard claims with evidence; rep verifies; Owner pays
R12 | Construction | Owner-furnished equipment supply | A | R | R | C |  | C |  |  |  | Interface and installation stay with the Yard under the contract
R13 | Construction | Workmanship inspections and punch list | I | R | R | C |  | A |  |  |  | The Yard owns quality; the owner's team inspects on the Owner's behalf
R14 | Trials and delivery | Harbour acceptance tests and sea trials | I | C | C | I | C | A/R | C | C |  | Class attends trials for its own rules; comfort criteria come from the contract
R15 | Trials and delivery | Crew recruitment, manning and safety management | A | C | R |  |  | I |  | C |  | Outside the builder's control
R16 | Trials and delivery | Acceptance and protocol of delivery | A | R | C | I |  | R | C | C |  | Owner signs; open punch items listed in the protocol
R17 | Trials and delivery | Registration and statutory certificates | R | C | C |  |  | R | R | A |  | Class works as RO where the flag has delegated
R18 | Warranty | Warranty claims in the first year | A: A; R: C; C: R; C: R |  | Lesson 24 covers the warranty year
Delegated authority of the owner's representative (illustrative; contract price = index 100)
Ref | Decision |  | A: Owner's rep may decide; C: Goes to the Owner |  | Notes
D01 | Owner change request, price effect |  | A: Up to 0.25 per request and 1.5 in total; C: Above either limit |  | Index points against contract price 100
D02 | Owner change request, delivery date effect |  | A: None; C: Any effect on the contractual delivery date
D03 | Change affecting GT budget, class notation or exterior profile |  | A: None; C: Always |  | Also needs naval architect check
D04 | Drawing comments within the approved specification |  | A: Yes, within the contractual review period; C: If the comment changes scope
D05 | Interior samples and finishes |  | A: Technical acceptance only; C: Look and feel always |  | Design Studio presents
D06 | Milestone completion certificate |  | A: Signs the technical certificate; C: Payment release |  | Evidence pack per Lesson 6
D07 | Acceptance at delivery |  | A: Recommends; C: Signs the protocol
D08
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.