## Read Me
TPL-SPM-T6 ¦ project2-me.com
Milestone Payment Plan and Evidence Tracker (T6)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From project2-me.com, lesson: Building the Milestone Payment Plan and Its Evidence Pack.
What is in this file
Blank: an empty payment plan (10 rows) with an evidence checklist (60 rows) underneath.
Example (YP-48, illustrative): the seven-payment plan and evidence checklist used in the lesson, shown at month 14.
How to use it
White cells are inputs. Grey cells are formulas: evidence items OK, cumulative share, paid to date, paid minus progress.
Shares are an index where the contract price = 100. Multiply by your own price outside this sheet if you need money values.
The check under the plan turns orange if the shares do not add up to 100, or if the security cover is below the amount paid.
Status: Planned > Claimed > Certified > Invoiced > Paid. Use Disputed while a claim is contested. Only Paid counts in Paid to date.
Evidence checklist: give each line the milestone number it belongs to. 'Evidence items OK' counts the lines marked Yes.
Est. physical progress is your own estimate of value built at the milestone month, on the same 0 to 100 index.
About the example
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
The payment shares are illustrative. There is no standard split for yacht milestone payments; yours is negotiated.
Milestone months come from the illustrative YP-48 master schedule (lesson: The Master Schedule for a Yacht Build).
Physical progress uses assumed weights per schedule activity, spread evenly over each activity.
Those weights are a teaching assumption, not data.
Class society and flag are not chosen in the example, so the text refers to 'class' and 'flag' in general terms.
This file is a planning aid, not legal advice. The contract and your counsel decide what a milestone requires.

## Blank
TPL-SPM-T6 ¦ project2-me.com
Milestone Payment Plan and Evidence Tracker
Index: contract price = 100. White cells are inputs, grey cells are formulas.
No | Payment milestone | Planned month | Completion definition (what must be true on the day) | Evidence required (details in the checklist below) | Yard responsible | Verified by | Survey / inspection ref. | Evidence items OK | Certificate signed (date) | Status | Share (index) | Cumulative share (index) | Paid to date (index) | Est. physical progress (index) | Paid minus progress | Payment date | Notes
Totals and checks
Shares total 100?
Paid to date (index)
Security cover in place (index)
Cover vs paid to date
Status as at
Evidence checklist: one line per document or record. Milestone no links each line to the plan above.
Milestone no | Evidence item | Type | What it must show | Provided by | Checked by | Received (date) | File / ref. | OK (Yes/No)

## Example (YP-48, illustrative)
TPL-SPM-T6 ¦ project2-me.com
YP-48 Milestone Payment Plan and Evidence Tracker (illustrative)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
No | Payment milestone | Planned month | Completion definition (what must be true on the day) | Evidence required (details in the checklist below) | Yard responsible | Verified by | Survey / inspection ref. | Evidence items OK | Certificate signed (date) | Status | Share (index) | Cumulative share (index) | Paid to date (index) | Est. physical progress (index) | Paid minus progress | Payment date | Notes
1 | Contract signature | 0 | Contract signed by both parties, and the refund guarantee issued in the wording annexed to the contract and received by the Owner's bank. | Signed contract; refund guarantee received via the Owner's bank; counsel's confirmation that the wording matches the annex; invoice. | Commercial director | Owner's counsel | n/a |  | Month 0 | Paid | 10 |  |  | 0 |  | Month 0 | First payment only after the guarantee is confirmed.
2 | Keel laying | 5 | Keel block K1 (as listed in the block plan annex) completed, set in its position in the hull assembly and tack-welded to the adjacent block, with class attendance recorded. | Joint inspection record; class attendance record; Yard dimensional check of K1; dated photo set with block ID visible. | Hull production manager | Owner's rep + class | Class visit ref. |  | Month 5 | Paid | 15 |  |  | 11 |  | Month 5 | Hull built inverted: this is a payment event, not a schedule driver (see L8).
3 | Main engines installed and aligned | 14 | Both main engines and gearboxes landed on their seatings, chocked and bolted; shaft lines fitted; alignment measured and recorded within the limits of the approved alignment calculation. Any afloat check required by the approved procedure belongs to the Launch milestone. | Alignment record signed by Yard and engine maker's engineer; chocking record; class attendance record; maker and class product certificates for engines and gearboxes; dated photo set. | Machinery manager | Owner's rep + class | Class visit ref. |  |  | Claimed | 15 |  |  | 54 |  |  | Illustrative status: one item still open, see checklist.
4 | Hull and superstructure joined | 16 | Aluminium superstructure landed on the hull and the steel-to-aluminium connection completed along its full length as per the approved drawing; NDT of the joint completed and accepted; class inspection of the joint closed with no open findings. | NDT reports for the joint; class inspection record; dimensional survey after joining; joint inspection record; dated photo set. | Hull production manager | Owner's rep + class |  |  |  | Planned | 15 |  |  | 62
5 | Launch | 24 | Yacht afloat and moored at the Yard, with every item on the pre-launch list in the contract annex complete: hull openings and sea valves fitted and tested, underwater coating complete, shafts, propellers and rudders fitted, bilge system operable; class records for these items attached. | Pre-launch list signed item by item; class records for listed items; launch record signed by both parties; draught readings after launch; dated photo set. | Project manager (Yard) | Owner's rep + class |  |  |  | Planned | 15 |  |  | 88 |  |  | Wording taken from the L5 review finding F-03.
6 | Sea trials complete | 28 | All tests in the agreed trial programme performed and recorded; results signed by the attending parties; each result within the contract tolerance, or the deviation recorded under the contract's deviation procedure; class trial attendance recorded. | Signed trial results log; speed, noise and vibration measurement reports; class trial record; deviation list with agreed actions. | Trials manager | Owner's rep + build captain + class |  |  |  | Planned | 10 |  |  | 98 |  |  | Trial programme itself: later lesson in this series.
7 | Delivery | 30 | Protocol of delivery and acceptance signed; class and flag certificates, builder's certificate and bill of sale handed over; open items list signed with each item classified, and no item open that the contract says blocks delivery. | Signed protocol; certificate list checked against originals; bill of sale; signed open items list; handover receipt for manuals, as-built drawings and spare parts. | Commercial director | Owner + Owner's rep |  |  |  | Planned | 20 |  |  | 100 |  |  | Any retention against open items is set in the contract, not here.
Totals and checks
Shares total 100?
Paid to date (index)
| Security cover in place (index) |  | 80
Cover vs paid to date
| Status as at |  | Month 14
Evidence checklist: one line per document or record. Milestone no links each line to the plan above.
Milestone no | Evidence item | Type | What it must show | Provided by | Checked by | Received (date) | File / ref. | OK (Yes/No)
1 | Signed contract with all annexes | Signed record | Both signatures; annex list complete | Yard | Owner's counsel | Month 0 | C-001 | Yes
1 | Refund guarantee | Certificate | Wording identical to the annexed form; amount covers pre-delivery instalments; expiry date | Yard's bank | Owner's counsel | Month 0 | RG-001 | Yes
1 | Invoice for instalment 1 | Commercial | Amount = share x contract price; bank details as contract | Yard | Owner's PM | Month 0 | INV-01 | Yes
2 | Joint inspection record, keel block K1 | Signed record | Block ID, position, alignment check, date; signed by both | Yard | Owner's rep | Month 5 | MS2-JIR | Yes
2 | Class attendance record | Class record | Class surveyor attended K1 erection | Yard | Owner's rep | Month 5 | MS2-CLS | Yes
2 | Dimensional check of K1 | Survey report | Measured values against tolerances on the approved drawing | Yard QA | Owner's rep | Month 5 | MS2-DIM | Yes
2 | Dated photo set | Photo set | Block ID visible; taken during the joint inspection | Yard | Owner's rep | Month 5 | MS2-PH | Yes
3 | Alignment record | Test record | Measured values within the approved alignment calculation; signed by Yard and maker's engineer | Yard | Owner's rep | Month 14 | MS3-ALN | Yes
3 | Chocking record | Test record | Chock material, thickness, bolt torque record for each engine and gearbox | Yard | Owner's rep | Month 14 | MS3-CHK | Yes
3 | Class attendance record | Class record | Installation inspected; open findings listed | Yard | Owner's rep | Month 14 | MS3-CLS | Yes
3 | Product certificates, engines and gearboxes | Certificate | Maker and class certificates match serial numbers installed | Yard | Owner's rep | Month 14 | MS3-CERT | Yes
3 | Joint inspection record | Signed record | Walk-down of both engine rooms; any open items listed | Yard | Owner's rep |  | MS3-JIR | No
3 | Dated photo set | Photo set | Both engines on seatings, shaft lines fitted | Yard | Owner's rep | Month 14 | MS3-PH | Yes
4 | NDT reports for the superstructure joint | Test record | Full length covered; acceptance by class | Yard QA | Owner's rep
4 | Class inspection record for the joint | Class record | No open findings | Yard | Owner's rep
4 | Dimensional survey after joining | Survey report | Values within the drawing tolerances | Yard QA | Owner's rep
4 | Joint inspection record | Signed record | Signed by both | Yard | Owner's rep
5 | Pre-launch list, signed item by item | Signed record | Every item in the annex closed | Yard | Owner's rep
5 | Class records for listed items | Class record | Sea valves, hull openings, shafts and rudders | Yard | Owner's rep
5 | Launch record and draught readings | Signed record | Afloat, moored, draughts read | Yard | Owner's rep
6 | Signed trial results log | Test record | Every test in the programme, signed by attendees | Yard | Owner's rep + build captain
6 | Measurement reports (speed, noise, vibration) | Test record | Method and conditions as the trial programme | Yard / measurement firm | Owner's rep
6 | Deviation list with agreed actions | Signed record | Each deviation classified and dated | Yard | Owner's rep
7 | Protocol of delivery and acceptance | Signed record | Signed by both parties | Yard | Owner
7 | Certificates (class, flag, builder's certificate) | Certificate | Originals seen and listed | Yard | Owner's counsel
7 | Bill of sale | Commercial | Form as required by the flag registry | Yard | Owner's counsel
7 | Signed open items list | Signed record | Each item classified; none that blocks delivery | Yard | Owner's rep
7 | Handover receipt: manuals, as-built drawings, spares | Signed record | Against the delivery documentation list | Yard | Build captain