## Read Me
TPL-SPM-T4 ¦ project2-me.com
Yard Bid Comparison Matrix (T4)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From project2-me.com, lesson: From Design Brief to Yard Shortlist: Outline Specification and Tender Package.
What is in this file
Blank: an empty matrix for up to five yards, eight price adjustments, six gates and fourteen criteria.
Example (YP-48, illustrative): three bids for the fictional 48 m yacht used in the lesson.
How to use it
White cells are inputs. Grey cells are formulas. Type the yard names once, in the Bid register header row.
Set the parameters, the gates, the criteria, the weights and the scoring guide before any bid is opened.
Bid register: enter each headline price, then one line per adjustment that makes the bids like for like.
Use + to add scope a yard left out (priced at your own estimate or the other bids), - to remove scope you did not ask for.
Gates: Pass or Fail. One Fail marks the yard Excluded; its score is still shown but it is not ranked.
Price score: a straight line from 10 at the floor to 0 at the ceiling. It does not depend on the other bids.
Other scores: 0 to 10, following the scoring guide column. Weighted = score x weight x 10, so the total is out of 100.
Weights must total 100%. The check turns orange if they do not, and the rank stays blank until they do.
Group subtotals show where each yard earns its score. Test the ranking by changing weights before you decide.
About the example
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Prices are an index where the YP-48 contract price = 100. Scores, weights and adjustments are a teaching example,
not an assessment of any real yard. Class society and flag are not chosen in the example.
This file is a decision aid, not legal or financial advice. Letters of intent and contracts need counsel.

## Blank
TPL-SPM-T4 ¦ project2-me.com
Yard Bid Comparison Matrix
Set parameters, gates, criteria and weights before bids are opened. White cells are inputs, grey cells are formulas.
Parameters (set before bids are opened)
Price scale floor: a like-for-like price at or below this scores 10
Price scale ceiling: a like-for-like price at or above this scores 0
Owner's target delivery (months from contract signature)
Bid register: headline price, like-for-like adjustments (+ adds missing scope, - removes extra scope), key terms
Ref | Item (yard names are typed in this row, columns F to O) |  |  |  | Yard 1 |  | Yard 2 |  | Yard 3 |  | Yard 4 |  | Yard 5
P1 | Headline bid price (index or currency, same unit for all yards)
A1
A2
A3
A4
A5
A6
A7
A8
P2 | Like-for-like price = headline + adjustments
D1 | Delivery offered (months from signature)
D2 | Delivery against the Owner's target (months, + = later)
D3 | First instalment at signature (% of price)
D4 | Bid validity / slot held until
Pass/fail gates: a single Fail excludes the yard before scoring
Ref | Gate
G1
G2
G3
G4
G5
G6
Gate result
Weighted scoring: scores 0 to 10, weights in %, weighted = score x weight x 10 (total out of 100)
Ref | Group | Criterion | Scoring guide (agree before bids open) | Weight |  | Weighted |  | Weighted |  | Weighted |  | Weighted |  | Weighted
C1 | Commercial | Like-for-like price (formula) | Formula: 10 at the floor, 0 at the ceiling, straight line between. Uses the like-for-like price, not the headline.
Total weight / weighted score out of 100
Weights total 100%?
Score counted for ranking (blank if excluded at the gates)
Rank (only when weights total 100%)
Subtotal: Technical
Subtotal: Commercial
Subtotal: Schedule
Subtotal: Risk
Notes per yard: red flags, open clarifications, conditions for the LOI
Topic
Main strengths
Red flags
Open clarifications
Conditions before an LOI

## Example (YP-48, illustrative)
TPL-SPM-T4 ¦ project2-me.com
YP-48 Yard Bid Comparison Matrix (illustrative)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Parameters (set before bids are opened)
Price scale floor: a like-for-like price at or below this scores 10 |  |  | 90
Price scale ceiling: a like-for-like price at or above this scores 0 |  |  | 110
Owner's target delivery (months from contract signature) |  |  | 30
Bid register: headline price, like-for-like adjustments (+ adds missing scope, - removes extra scope), key terms
Ref | Item (yard names are typed in this row, columns F to O) |  |  |  | Yard A |  | Yard B |  | Yard C |  | Yard 4 |  | Yard 5
P1 | Headline bid price (index or currency, same unit for all yards) |  |  |  | 92 |  | 97 |  | 103.5
A1 | AV/IT allowance raised to the Owner's figure |  |  |  | 2.5 |  | 0 |  | 0
A2 | Loose furniture allowance raised to the Owner's figure |  |  |  | 0 |  | 1.5 |  | 0
A3 | Stabilisers with zero-speed function, as the outline spec requires |  |  |  | 1.5 |  | 0 |  | 0
A4 | Tender garage crane quoted as an option, added |  |  |  | 0 |  | 1 |  | 0
A5 | Class and flag approval fees excluded, added |  |  |  | 0.5 |  | 0 |  | 0
A6 | Trial costs and crew familiarisation excluded, added |  |  |  | 1 |  | 0.5 |  | 0
A7 | Two tenders included that the Owner buys directly, removed |  |  |  | 0 |  | 0 |  | -2
A8
P2 | Like-for-like price = headline + adjustments
D1 | Delivery offered (months from signature) |  |  |  | 34 |  | 30 |  | 36
D2 | Delivery against the Owner's target (months, + = later)
D3 | First instalment at signature (% of price) |  |  |  | 20 |  | 10 |  | 15
D4 | Bid validity / slot held until |  |  |  | 8 weeks |  | 8 weeks |  | 6 weeks
Pass/fail gates: a single Fail excludes the yard before scoring
Ref | Gate
G1 | Can build and certify to REG Yacht Code Part A below 500 GT (GT estimate from the yard's naval architect) |  |  |  | Pass |  | Pass |  | Pass
G2 | Refund guarantee from a bank acceptable to the Owner, or security counsel accepts |  |  |  | Pass |  | Pass |  | Pass
G3 | Delivery no later than month 36 from signature |  |  |  | Pass |  | Pass |  | Pass
G4 | Site access for the owner's representative and build captain |  |  |  | Pass |  | Pass |  | Pass
G5
G6
Gate result
Weighted scoring: scores 0 to 10, weights in %, weighted = score x weight x 10 (total out of 100)
Ref | Group | Criterion | Scoring guide (agree before bids open) | Weight |  | Weighted |  | Weighted |  | Weighted |  | Weighted |  | Weighted
C1 | Commercial | Like-for-like price (formula) | Formula: 10 at the floor, 0 at the ceiling, straight line between. Uses the like-for-like price, not the headline. | 20%
T1 | Technical | Compliance with the outline specification (deviations list) | 10: no deviations. 5: deviations priced and acceptable. 0: key requirements not met. | 15% | 6 |  | 8 |  | 9
T2 | Technical | Comparable yachts delivered (size, GT, code) | 10: several comparable yachts in the last 10 years, same code and GT band. 0: none. | 10% | 5 |  | 8 |  | 9
T3 | Technical | Engineering capacity and proposed makers list | 10: in-house engineering sized for the job, makers list matches the spec. 0: engineering not resourced. | 5% | 6 |  | 7 |  | 8
C2 | Commercial | Payment schedule and security offered | 10: back-loaded payments, on-demand refund guarantee from first instalment. 0: front-loaded, security weak. | 10% | 5 |  | 7 |  | 8
S1 | Schedule | Delivery date against the Owner's target | 10: on or before target. Minus 1.5 per month late (guide, not a formula). | 10% | 4 |  | 8 |  | 3
S2 | Schedule | Slot credibility (order book, hull source, concurrent builds) | 10: slot evidenced by order book and shed plan, hull built in house. 0: slot depends on other builds finishing. | 10% | 4 |  | 7 |  | 6
R1 | Risk | Financial strength and refund guarantee capacity | 10: audited accounts reviewed, bank confirms guarantee capacity. 0: no evidence. | 10% | 4 |  | 7 |  | 8
R2 | Risk | Mark-up of the Owner's key contract terms | 10: key terms accepted. 0: key terms rejected. | 5% | 5 |  | 6 |  | 5
R3 | Risk | Reference checks with owners and captains | 10: owners and captains confirm quality, time and cooperation. 0: negative or refused. | 5% | 6 |  | 8 |  | 8
Total weight / weighted score out of 100
Weights total 100%?
Score counted for ranking (blank if excluded at the gates)
Rank (only when weights total 100%)
Subtotal: Technical
Subtotal: Commercial
Subtotal: Schedule
Subtotal: Risk
Notes per yard: red flags, open clarifications, conditions for the LOI
Topic
| Main strengths |  |  |  | Lowest headline price |  | Delivery on target; comparable 45 to 50 m yachts delivered |  | Strongest technical offer; 24-month warranty offered
| Red flags |  |  |  | Hull built at a subcontract yard; slot follows a current build; refund guarantee bank not yet named |  | Loose furniture allowance set low in the bid |  | Next free slot gives delivery at month 36; material escalation clause
| Open clarifications |  |  |  | Bank letter for the guarantee; shed plan for months 1 to 12 |  | Makers list alternatives for stabilisers |  | Can the slot move earlier?
| Conditions before an LOI |  |  |  | Not proposed for LOI |  | Slot held for 8 weeks; exclusivity; deposit terms agreed by counsel |  | Kept as reserve while the LOI with Yard B runs