## Read Me
TPL-SPM-T7 ¦ project2-me.com
Drawing Approval Register and Weight / GT Tracker (T7)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From project2-me.com, lesson: Specification, General Arrangement and the Design Freeze.
What is in this file
Register - Blank: one row per drawing or document that needs a reply, 80 rows.
Weight & GT - Blank: gross tonnage and lightship weight budget with a change log, 60 rows.
Register - Example YP-48 and Weight & GT - Example YP-48: the worked example from the lesson (illustrative).
Register: how to use it
White cells are inputs, grey cells are formulas. Enter the 'As at' date at the top before reading the counters.
Due date = submitted + review period. Use calendar days if that is what your contract says; otherwise adjust.
Status comes from the response code: A approved, B approved with comments, C revise and resubmit, I for information.
With no reply after the due date, Status shows 'Overdue', or 'Deemed approval?' where you marked deemed approval as allowed.
'Deemed approval?' is a prompt to check the contract clause, not a legal conclusion.
Days late compares the reply (or today's 'As at' date) with the due date. Float to need compares it with the date the drawing is needed.
A negative float to need means the reply arrives after the work that depends on it should start.
For class-only items the review period is your planning assumption: class works to its own procedure.
'Departs from spec?' = Yes means the drawing changes what the specification says. Route it as a change, not as a drawing comment.
Weight & GT: how to use it
Enter the starting estimates, the target and limit, the budget and warning margins at the top.
Log every change or estimate update with its GT and weight effect from the naval architect. Only 'Accepted...' rows count.
The rule-of-thumb column multiplies added enclosed volume by 0.274 GT per m3. That factor comes from the ITC 1969 gross tonnage formula near 490 to 500 GT and only shows scale. It is not a tonnage calculation.
Weight is an index (estimate at signature = 100). Replace with tonnes if your naval architect reports tonnes.
About the example
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
All drawing numbers, dates, review periods, GT and weight figures are illustrative. The notional contract date is 2027-01-04.
The register example is shown as at 2027-10-04 (about month 9); the weight and GT example as at month 14.
Class society and flag are not chosen in the example, so the text refers to 'class' and 'flag' in general terms.
This file is a planning aid, not legal or naval architecture advice. The contract, class, the flag and your naval architect decide.

## Register - Blank
TPL-SPM-T7 ¦ project2-me.com
Drawing and Document Approval Register
White cells are inputs, grey cells are formulas. Set the 'As at' date first.
| As at (date) | [8 empty] | Drawings listed |  |  | Overdue, no reply
| Design freeze (date) | [8 empty] | Not submitted |  |  | Deemed approval to check
| Codes: A approved, B approved with comments, C revise and resubmit, I for information. | [8 empty] | Under review |  |  | Reply after need date
[10 empty] | Approved (A or B) |  |  | Departs from spec
Resubmit (C)
No | Drawing / document no | Title | Discipline | Approval route | Rev | Submitted (date) | Review period (days) | Due date | Needed by (date) | Needed for (schedule activity) | Response received (date) | Response code (A/B/C/I) | Class / flag status (dual-route items) | Deemed approval allowed? | Status | Days late vs review period | Float to need (days) | Departs from spec? | Frozen item (after design freeze)? | Comments ref / notes

## Weight & GT - Blank
TPL-SPM-T7 ¦ project2-me.com
Weight and Gross Tonnage Tracker
White cells are inputs, grey cells are formulas. GT effects come from your naval architect.
|  | GT estimate at signature |  |  | Weight at signature (index) | 100 |  | Current GT estimate |  |  | Current weight (index)
|  | GT target |  |  | Weight budget (index) |  |  | GT margin to target |  |  | Weight margin left
|  | GT limit (must stay below) |  |  | Weight warning margin |  |  | Headroom to GT limit |  |  | Weight check
|  | GT warning margin |  |  | Design freeze (month) |  |  | GT check |  |  | Weight margin if pending accepted
[5 empty] | As at (month) |  |  | GT margin if pending accepted |  |  | Changes after freeze (count)
GT effect: the naval architect's figure. The rule-of-thumb column only shows scale near 490 to 500 GT (ITC 1969 formula); it does not replace a tonnage calculation or the official measurement.
Only rows whose Decision starts with 'Accepted' count in the running totals. Pending items are shown in the 'if pending accepted' cells.
No | Month | Ref | Change or estimate update | Raised by | Added enclosed volume (m3) | GT effect (naval architect) | Rule-of-thumb GT (volume x 0.274) | Weight effect (index points) | Decision | Counts? | Running GT estimate | GT margin to target | Running weight (index) | Weight margin left | After design freeze? | Notes

## Register - Example YP-48
TPL-SPM-T7 ¦ project2-me.com
YP-48 Drawing and Document Approval Register (illustrative)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
| As at (date) | 2027-10-04 | [7 empty] | Drawings listed |  |  | Overdue, no reply
| Design freeze (date) | 2027-08-02 | [7 empty] | Not submitted |  |  | Deemed approval to check
| Codes: A approved, B approved with comments, C revise and resubmit, I for information. | [8 empty] | Under review |  |  | Reply after need date
[10 empty] | Approved (A or B) |  |  | Departs from spec
Resubmit (C)
No | Drawing / document no | Title | Discipline | Approval route | Rev | Submitted (date) | Review period (days) | Due date | Needed by (date) | Needed for (schedule activity) | Response received (date) | Response code (A/B/C/I) | Class / flag status (dual-route items) | Deemed approval allowed? | Status | Days late vs review period | Float to need (days) | Departs from spec? | Frozen item (after design freeze)? | Comments ref / notes
1 | YP48-000-001 | Technical specification, post-signature issue | General | Owner | B | 2027-01-18 | 14 |  |  |  | 2027-01-29 | A |  | Yes |  |  |  | No | No | Incorporates the agreed contract-review changes
2 | YP48-100-001 | General arrangement | General | Owner+Class | D | 2027-06-21 | 14 |  | 2027-08-02 | Design freeze | 2027-07-02 | B | Approved | Yes |  |  |  | No | No | Rev D is the freeze GA once B comments are in rev E
3 | YP48-100-002 | Preliminary tonnage and volume calculation | Naval arch. | Owner | B | 2027-06-28 | 14 |  | 2027-08-02 | Design freeze | 2027-07-09 | A |  | Yes |  |  |  | No | No | Estimate 493.9 GT at freeze
4 | YP48-100-003 | Lightship weight estimate, update 3 | Naval arch. | Owner | C | 2027-08-16 | 14 | [6 empty] | Yes |  |  |  | No | No | No reply yet: check before the deemed date passes
5 | YP48-200-001 | Midship section and scantlings | Hull | Owner+Class | A | 2027-02-15 | 14 |  | 2027-05-03 | Start of steel cutting | 2027-02-26 | A | Approved | Yes |  |  |  | No | No
6 | YP48-200-010 | Shell expansion | Hull | Class | 1 | 2027-03-08 | 30 |  | 2027-05-03 | Start of steel cutting | 2027-04-02 | A |  | No |  |  |  | No | No | Class period is the Yard's planning assumption
7 | YP48-200-020 | Aluminium superstructure structure | Hull | Owner+Class | C | 2027-05-17 | 14 |  | 2027-09-01 | Aluminium superstructure | 2027-05-28 | A | Approved with comments | Yes |  |  |  | No | No | Rev B returned C by owner (window framing); rev C approved
8 | YP48-200-030 | Superstructure to hull connection detail | Hull | Owner+Class | A | 2027-08-09 | 14 |  | 2028-04-03 | Join superstructure to hull | 2027-08-20 | B | Pending | Yes |  |  |  | No | No
9 | YP48-300-001 | Machinery arrangement | Machinery | Owner+Class | B | 2027-05-24 | 14 |  | 2027-12-01 | Main engine installation | 2027-06-04 | B | Approved with comments | Yes |  |  |  | No | No
10 | YP48-300-010 | Shafting arrangement and alignment calculation | Machinery | Class | A | 2027-07-05 | 30 |  | 2028-01-03 | Main engine installation |  |  |  | No |  |  |  | No | No | Chased with class at weekly meeting
11 | YP48-400-001 | Electrical load balance | Electrical | Owner+Class | A | 2027-07-19 | 14 |  | 2027-12-01 | Piping, HVAC, electrical and cabling | 2027-07-30 | A | Pending | Yes |  |  |  | No | No
12 | YP48-500-001 | Fire control and escape plan | Safety | Owner+Class | A | 2027-06-28 | 14 |  | 2027-08-02 | Design freeze | 2027-07-09 | A | Approved with comments | Yes |  |  |  | No | No | Code items via class acting as RO (illustrative split)
13 | YP48-500-010 | Structural fire protection plan | Safety | Class | A | 2027-08-02 | 30 |  | 2027-12-01 | Piping, HVAC, electrical and cabling | 2027-09-24 | B |  | No |  |  |  | No | No
14 | YP48-600-001 | Interior layout, lower deck guest cabins | Interior | Owner | C | 2027-06-14 | 21 |  | 2027-08-02 | Design freeze | 2027-07-02 | A |  | No |  |  |  | No | No
15 | YP48-600-002 | Interior layout, main deck and owner's suite | Interior | Owner | D | 2027-07-12 | 21 |  | 2027-08-02 | Design freeze | 2027-07-30 | B |  | No |  |  |  | No | No
16 | YP48-600-020 | Master bathroom: stone finish and colour | Interior | Owner | A | 2027-08-09 | 21 |  | 2027-11-01 | Interior detail design |  |  |  | No |  |  |  | No | Yes | Finish and colour: no deemed approval in the YP-48 contract
17 | YP48-600-030 | Guest cabin joinery details | Interior | Owner |  |  | 21 |  | 2027-11-01 | Interior detail design |  |  |  | No |  |  |  | No | Yes | Planned submission 2027-10-11
18 | YP48-700-001 | Exterior glazing arrangement | Exterior | Owner+Class | B | 2027-06-07 | 14 |  | 2027-08-02 | Glazing order (after freeze) | 2027-06-18 | A | Approved | Yes |  |  |  | No | No
19 | YP48-700-010 | Wheelhouse arrangement (VO-02 deckhead) | Exterior | Owner+Class | B | 2027-09-27 | 14 |  | 2027-11-01 | Aluminium superstructure |  |  | Pending | Yes |  |  |  | No | Yes | Post-freeze change: VO-02 signed before submission
20 | YP48-000-010 | Makers list: proposed equivalent navigation package | General | Owner | 1 | 2027-09-13 | 14 |  | 2028-01-03 | AV/IT and navigation order | 2027-09-24 | A |  | No |  |  |  | Yes | No | Equivalence accepted in writing, logged as a no-cost change

## Weight & GT - Example YP-48
TPL-SPM-T7 ¦ project2-me.com
YP-48 Weight and Gross Tonnage Tracker (illustrative)
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
|  | GT estimate at signature | 488 |  | Weight at signature (index) | 100 |  | Current GT estimate |  |  | Current weight (index)
|  | GT target | 499 |  | Weight budget (index) | 105 |  | GT margin to target |  |  | Weight margin left
|  | GT limit (must stay below) | 500 |  | Weight warning margin | 1 |  | Headroom to GT limit |  |  | Weight check
|  | GT warning margin | 3 |  | Design freeze (month) | 7 |  | GT check |  |  | Weight margin if pending accepted
[5 empty] | As at (month) | 14 |  | GT margin if pending accepted |  |  | Changes after freeze (count)
GT effect: the naval architect's figure. The rule-of-thumb column only shows scale near 490 to 500 GT (ITC 1969 formula); it does not replace a tonnage calculation or the official measurement.
Only rows whose Decision starts with 'Accepted' count in the running totals. Pending items are shown in the 'if pending accepted' cells.
No | Month | Ref | Change or estimate update | Raised by | Added enclosed volume (m3) | GT effect (naval architect) | Rule-of-thumb GT (volume x 0.274) | Weight effect (index points) | Decision | Counts? | Running GT estimate | GT margin to target | Running weight (index) | Weight margin left | After design freeze? | Notes
1 | 0 | BASE | Estimate at contract signature (contract GA and specification) | Naval architect |  | 0 |  | 0 | Accepted | [6 empty] | Starting point; values in the inputs above
2 | 2 | NA-01 | Basic design: hull form faired, tank arrangement updated | Naval architect |  | 1.2 |  | 0.6 | Accepted
3 | 3 | CR-01 | Owner: enclosed gym on bridge deck aft, reduced from 4.0 x 3.0 m to 3.0 x 2.5 m, 2.3 m high (17.25 m3) | Owner | 17.2 | 4.7 |  | 0.5 | Accepted as reduced | [6 empty] | Proposed 4.0 x 3.0 m (27.6 m3, about 7.6 GT); reduced after tonnage check
4 | 5 | CL-01 | Class plan approval comments: heavier structure around the tender garage opening | Class |  | 0 |  | 0.7 | Accepted | [6 empty] | Weight only: structure does not change enclosed volume
5 | 6 | ID-01 | Interior layout: stone floors in master and guest bathrooms | Design Studio |  | 0 |  | 0.9 | Accepted
6 | 9 | VO-02 | Owner: wheelhouse deckhead raised 150 mm over 38 m2 (5.7 m3), after design freeze | Owner | 5.7 | 1.6 |  | 0.2 | Accepted as VO | [6 empty] | After freeze: priced and signed as a variation order
7 | 11 | NA-02 | Detail engineering: service spaces and casings updated | Naval architect |  | 0.8 |  | 0.4 | Accepted
8 | 12 | PK-01 | Joinery package: supplier weight estimate above allowance | Yard |  | 0 |  | 1.1 | Accepted
9 | 14 | CR-05 | Owner: enclosed sun-deck bar, 4.0 x 2.5 m, 2.3 m high (23.0 m3) | Owner | 23 | 6.3 |  | 0.6 | Rejected | [6 empty] | Would take the estimate to about 502.6 GT, over the 500 GT line
10 | 14 | CR-06 | Owner: larger hydraulic tender garage door | Owner |  | 0 |  | 0.3 | Pending | [6 empty] | Awaiting Yard price and naval architect check