## Read Me
TPL-SPM-T9 ¦ project2-me.com
Owner Change Request Form and Change / VO Log (T9)
How to use this workbook. Not legal advice: the contract's change clause and your counsel decide.
What it is
An owner-side change control workbook for a yacht newbuild: a one-page change request form and a change / variation order log with cumulative totals and an authority check against the owner's representative's limits.
It sits beside, not in place of, the Yard's variation order. The site's Variation Order Form and Cost Impact Calculation Sheet cover the priced VO and its cost build-up.
Sheets
Change Log - Blank / Change Log - Example YP-48: one row per request, in the order raised.
CR Form - Blank / CR Form - Example CR-06: the request form, printable on A4.
How to use the log
1. Fill the parameters at the top: as-at date, GA design freeze date, contractual delivery date, and the representative's limits from your delegation letter (index, contract price = 100, or replace with your currency).
2. Enter each request when it is raised, even if it is later rejected. Rejected requests are part of the record.
3. Enter the Yard's proposal (price, delivery days) and, once signed, the agreed figures. Write 0 when the agreed delivery effect is nil; a blank is flagged, because 'time to be advised' is how cumulative time claims start.
4. GT and weight effects come from the naval architect. Carry the running margins in the T7 Weight & GT tracker.
5. Grey columns are formulas: before/after freeze, required approval level, cumulative signed price and days, the representative's signed total, an authority check and days open. Do not type over them.
Required approval level (formula)
Owner if the change has any delivery date effect, any GT effect, affects class/flag or the exterior profile, or is a credit (deleted scope). Otherwise Owner's rep if the price is within the per-request limit and the representative's signed total stays within the cumulative limit; else Owner. Adapt the formula in column P to your own letter.
Statuses
Raised, Screening, RFP sent, Priced, Signed, Disputed (proceeding), Rejected, Withdrawn, Deferred. Pending exposure counts Priced and Disputed items at the Yard's proposed price.
Example data
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
All money is an index (contract price = 100). GT and weight effects match the T7 example for the same project.
Limits
Not legal advice. The contract's change clause, notice periods and signatories prevail over anything in this workbook.

## Change Log - Blank
TPL-SPM-T9 ¦ project2-me.com
Owner Change Request Form and Change / VO Log (T9)
Blank log. Index: contract price = 100 (or your currency). Enter your own delegation limits.
|  | As at (date) |  |  |  |  | Requests logged |  |  | Signed price total (index) |  |  | Agreed delivery days |  |  | Authority flags
|  | GA design freeze (date) |  |  |  |  | Signed |  |  | Pending exposure (index) |  |  | Days claimed, not agreed |  |  | Changes after GA freeze
|  | Contractual delivery date |  |  |  |  | Open (raised to priced) |  |  | Total if pending accepted |  |  | Forecast delivery (agreed days)
|  | Rep's limit per request (index) | 0.25 |  |  |  | Disputed (proceeding) |  |  | Signed GT effect |  |  | Rep's signed total (index)
|  | Rep's cumulative limit (index) | 1.5 |  |  |  | Rejected / withdrawn / deferred |  |  | Signed weight effect |  |  | Rep's limit left (index)
Index: contract price = 100. White cells are inputs; grey cells are formulas.
CR no | Date raised | Raised by | Description of the change | Area / system | Before / after GA freeze | Yard VO ref | Price, Yard proposal (index) | Price, agreed (index) | Delivery days, Yard proposal | Delivery days, agreed | GT effect | Weight effect (index) | Class / flag or exterior profile affected? | Changes a payment milestone? | Required approval level | Approved by | Decision date | Status | Cumulative signed price (index) | Cumulative agreed days | Owner's rep signed total (index) | Authority check | Days open | Notes

## Change Log - Example YP-48
TPL-SPM-T9 ¦ project2-me.com
Owner Change Request Form and Change / VO Log (T9)
Example, as at month 15. Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
|  | As at (date) | 2028-04-03 |  |  |  | Requests logged |  |  | Signed price total (index) |  |  | Agreed delivery days |  |  | Authority flags
|  | GA design freeze (date) | 2027-08-02 |  |  |  | Signed |  |  | Pending exposure (index) |  |  | Days claimed, not agreed |  |  | Changes after GA freeze
|  | Contractual delivery date | 2029-07-16 |  |  |  | Open (raised to priced) |  |  | Total if pending accepted |  |  | Forecast delivery (agreed days)
|  | Rep's limit per request (index) | 0.25 |  |  |  | Disputed (proceeding) |  |  | Signed GT effect |  |  | Rep's signed total (index)
|  | Rep's cumulative limit (index) | 1.5 |  |  |  | Rejected / withdrawn / deferred |  |  | Signed weight effect |  |  | Rep's limit left (index)
Index: contract price = 100. White cells are inputs; grey cells are formulas.
CR no | Date raised | Raised by | Description of the change | Area / system | Before / after GA freeze | Yard VO ref | Price, Yard proposal (index) | Price, agreed (index) | Delivery days, Yard proposal | Delivery days, agreed | GT effect | Weight effect (index) | Class / flag or exterior profile affected? | Changes a payment milestone? | Required approval level | Approved by | Decision date | Status | Cumulative signed price (index) | Cumulative agreed days | Owner's rep signed total (index) | Authority check | Days open | Notes
CR-01 | 2027-04-05 | Owner | Enclosed gym on bridge deck aft; reduced from 4.0 x 3.0 m to 3.0 x 2.5 m after the tonnage check | Exterior / superstructure |  | VO-01 | 0.45 | 0.4 | 0 | 0 | 4.7 | 0.5 | Yes | No |  | Owner | 2027-05-10 | Signed | [5 empty] | Before the freeze and before superstructure steel: drawings only
CR-02 | 2027-09-06 | Owner | Wheelhouse deckhead raised 150 mm over 38 m2 | Exterior / superstructure |  | VO-02 | 0.62 | 0.55 | 15 | 0 | 1.6 | 0.2 | Yes | No |  | Owner | 2027-09-24 | Signed | [5 empty] | After the freeze: wheelhouse glazing order revised; Yard resequenced the wheelhouse modules, 0 days agreed
CR-03 | 2027-10-11 | Captain (via owner's rep) | Move the engine room switch panel to the forward bulkhead | Machinery / electrical |  | VO-03 | 0.06 | 0.06 | 0 | 0 | 0 | 0 | No | No |  | Owner's rep | 2027-10-25 | Signed | [5 empty] | Within the representative's limits
CR-04 | 2027-12-06 | Owner | Sky lounge cinema system (screen, projector lift, speakers) | Interior / AV-IT |  | VO-04 | 0.42 | 0.4 | 0 | 0 | 0 | 0 | No | No |  | Owner | 2028-01-10 | Signed | [5 empty] | Yard first offered two VOs of 0.21 each; merged into one and sent to the Owner
CR-05 | 2028-02-23 | Owner | Enclosed bar on the sun deck, 4.0 x 2.5 m | Exterior / superstructure | [6 empty] | 6.3 | 0.6 | Yes | No |  | Owner | 2028-03-01 | Rejected | [5 empty] | Screened before pricing: GT estimate would reach about 502.6
CR-06 | 2028-02-28 | Owner | Larger hydraulic tender garage door | Hull / exterior |  | VO-06 (proposal) | 0.7 |  | 21 |  | 0 | 0.3 | Yes | Yes |  |  |  | Priced | [5 empty] | Offer valid to 2028-04-10; hull welding must finish before hot work complete (2028-05-10)
CR-07 | 2028-03-20 | Owner | Delete the sauna in the owner's suite (credit) | Interior |  | VO-07 | -0.1 |  | 0 |  | 0 | -0.1 | No | No |  | Owner | 2028-03-27 | Disputed (proceeding) | [5 empty] | Owner's side values the credit at -0.22; Owner instructed the deletion, value to the expert route
CR-08 | 2028-03-27 | Owner's rep | Blackout blinds in the four guest cabins | Interior |  | VO-08 (proposal) | 0.15 |  | 0 |  | 0 | 0 | No | No |  |  |  | Priced | [5 empty] | Within the representative's limits; decision due this week

## CR Form - Blank
TPL-SPM-T9 ¦ project2-me.com
Owner Change Request Form (T9)
Blank request form. One per change request.
One form per request. Owner-side record; the priced change itself is the Yard's variation order.
REQUEST
CR number
Date raised
Raised by
Submitted through (owner's rep)
Description of the change (what, where, drawing and specification references)
Reason
What happens if the change is not made; alternatives considered
Decision needed by (date and why)
SCREENING (owner's side, before asking the Yard to price)
Is it a change? (not design development inside the specification, not a defect)
Frozen layer affected (hull, superstructure, GA / interior layout, interior details)
GT and weight: first estimate and source
Hot-work cut-off, paint window or long-lead order affected?
Screening result (send for pricing / reject / withdraw)
YARD PROPOSAL (from the Yard's VO; copy the figures here)
Request for proposal sent (date)
Yard VO reference
Price (index, contract price = 100)
Delivery date effect (days)
GT effect / weight effect (naval architect)
Payment milestone wording affected?
Class / flag approval needed?
Proposal valid until
DECISION
Required approval level (delegation letter)
Decision (approve / reject / defer) and conditions
Owner's rep: name, signature, date
Owner: name, signature, date (where required)
Entered in the change log (date, row)

## CR Form - Example CR-06
TPL-SPM-T9 ¦ project2-me.com
Owner Change Request Form (T9)
Example (YP-48, illustrative): CR-06 as at 2028-04-03. Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
One form per request. Owner-side record; the priced change itself is the Yard's variation order.
REQUEST
CR number | CR-06
Date raised | 2028-02-28
Raised by | Owner
Submitted through (owner's rep) | Owner's representative
Description of the change (what, where, drawing and specification references) | Replace the tender garage door with a larger hydraulic door so the new limousine tender fits. Affects the hull opening and door drawings (garage area) and the specification section on the tender garage.
Reason | Owner preference: larger tender chosen after contract signature.
What happens if the change is not made; alternatives considered | Without it the current tender size stays; alternative considered: smaller tender, no change to the hull.
Decision needed by (date and why) | 2028-04-10 (Yard's offer validity); hull welding must finish before hot work complete, 2028-05-10.
SCREENING (owner's side, before asking the Yard to price)
Is it a change? (not design development inside the specification, not a defect) | Yes. The specification describes the current door size.
Frozen layer affected (hull, superstructure, GA / interior layout, interior details) | Hull structure (fixed at steel cutting). Exterior profile changes slightly.
GT and weight: first estimate and source | No enclosed volume added: GT 0. Weight about +0.3 (index) per naval architect's first estimate; weight margin 0.6 left.
Hot-work cut-off, paint window or long-lead order affected? | Yes: welding in the hull opening before the hot-work cut-off; paint window starts after it.
Screening result (send for pricing / reject / withdraw) | Send for pricing. Goes to the Owner in any case (class, exterior profile, weight).
YARD PROPOSAL (from the Yard's VO; copy the figures here)
Request for proposal sent (date) | 2028-02-29
Yard VO reference | VO-06 (proposal)
Price (index, contract price = 100) | 0.70
Delivery date effect (days) | 21 (Yard proposal)
GT effect / weight effect (naval architect) | GT 0.0 / weight +0.3
Payment milestone wording affected? | Yes: the pre-launch list gets the new door and its test.
Class / flag approval needed? | Yes: revised opening and door structure to class for plan approval.
Proposal valid until | 2028-04-10
DECISION
Required approval level (delegation letter) | Owner (delivery date, class and exterior profile effects)
Decision (approve / reject / defer) and conditions | Open as at 2028-04-03. Owner's side to test the 21 days against the current schedule before deciding.
Owner's rep: name, signature, date
Owner: name, signature, date (where required)
Entered in the change log (date, row) | Change log row CR-06