## Read me
TPL-SPM-T10 ¦ project2-me.com
T10 Physical Progress Calculator
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
What it does
Turns activity weights and percentages complete into one physical progress figure on a 0 to 100 scale, compares it with the plan, and keeps a monthly log that draws the S-curve and the progress index.
How to use it
1. List your activities (WBS code, name, group) and give each a weight. Weights must total 100 (check cell).
2. Write the rule of credit for each activity (for example: steps ordered 10 / drawings 20 / FAT 30 / at yard 40).
3. Mark critical-path activities with Y (from your live schedule).
4. Each month enter planned % (from the baseline, using the same rule of credit) and measured % with an evidence reference.
5. Copy the month's totals into the monthly log. The charts redraw. The index is left blank while planned is below 10.
Colours
Index status uses the thresholds at the top of each sheet (YP-48 example: green 0.97 and above, red below 0.90). Agree your own thresholds with the Owner. The index supports the schedule rating; it does not replace the critical-path forecast.
Sheets
Blank: empty activity table (30 lines) and a 37-month log. Example (YP-48, illustrative): the month-14 measurement used in the lesson.
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Planned values in the example come from the YP-48 baseline schedule and teaching weights; measured values are invented for teaching.
White cells are inputs. Grey cells are formulas.

## Blank
TPL-SPM-T10 ¦ project2-me.com
T10 Physical Progress Calculator
Enter weights, rules of credit and percentages. Weights total 100.
Measurement month |  |  |  | Weights total (must be 100)
Index green at or above |  | 0.97 |  | Total planned / measured
Index red below |  | 0.9 |  | Physical progress index / status
Critical lines behind plan
WBS | Activity | Group | Weight | Rule of credit | Critical (Y/N) | Planned % | Measured % | Evidence ref | Planned value | Measured value | Variance | Index | Flag
Total
Monthly log (copy the month's totals here; the charts redraw)
Month | Planned (cumulative) | Measured (cumulative) | Index
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## Example (YP-48, illustrative)
TPL-SPM-T10 ¦ project2-me.com
T10 Physical Progress Calculator
Example (YP-48, illustrative): month-14 measurement. Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Measurement month |  | 14 |  | Weights total (must be 100)
Index green at or above |  | 0.97 |  | Total planned / measured
Index red below |  | 0.9 |  | Physical progress index / status
Critical lines behind plan
WBS | Activity | Group | Weight | Rule of credit | Critical (Y/N) | Planned % | Measured % | Evidence ref | Planned value | Measured value | Variance | Index | Flag
2.1 | Basic design and class/flag plan approval | Design and engineering | 4 | Drawings approved / drawings on list | Y | 100 | 100 | Register T7, all basic design items approved
2.3 | Detail and production engineering | Design and engineering | 5 | Drawings issued for production / list | Y | 100 | 95 | Register T7, 6 production drawings not yet issued
2.4 | Interior detail design and sample approval | Design and engineering | 2 | Interior drawings and samples approved / list | N | 100 | 85 | Two stone samples and AV/IT spec awaiting Owner
3.1 | Propulsion package: order to delivery | Long-lead equipment and packages | 8 | Steps: ordered 10, drawings 20, FAT 30, at yard 40 | N | 100 | 100 | Delivery notes, month 12
3.2 | Generator sets: order to delivery | Long-lead equipment and packages | 4 | Steps: ordered 10, drawings 20, FAT 30, at yard 40 | N | 100 | 100 | Delivery notes, month 13
3.3 | Stabilizers: order to delivery | Long-lead equipment and packages | 3 | Steps: ordered 10, drawings 20, FAT 30, at yard 40 | N | 100 | 100 | Delivery notes, month 13
3.4 | Glazing and exterior doors: order to delivery | Long-lead equipment and packages | 3 | Steps: ordered 10, drawings 20, FAT 30, at yard 40 | N | 77.8 | 60 | FAT passed month 13; delivery due month 16
3.5 | Interior joinery package: award and prefabrication | Long-lead equipment and packages | 4 | Joinery units prefabricated / units | N | 100 | 85 | Joinery unit count, subcontractor sheet
3.6 | AV/IT and navigation: order to delivery | Long-lead equipment and packages | 3 | Steps: ordered 10, drawings 20, FAT 30, at yard 40 | N | 0 | 0 | Order waits for Owner's spec sign-off
4.2 | Steel hull construction (built inverted, turned) | Hull and superstructure | 12 | Hull sections welded and inspected (weighted by steel weight) | Y | 100 | 100 | Hull complete, month 11
4.4 | Aluminium superstructure construction | Hull and superstructure | 6 | Superstructure sections welded and inspected (weighted by weight) | Y | 85.7 | 78 | Section list, 2 sections still to weld and inspect
4.5 | Join superstructure to hull | Hull and superstructure | 2 | 0/100: joint welded, NDT and class record closed | Y | 0 | 0 | Not started (planned month 15)
5.1 | Main engine and gearbox installation and alignment | Systems installation | 2 | Steps: landed 40, chocked 30, aligned and recorded 30 | N | 100 | 100 | Alignment record MS3-ALN; milestone claimed
5.3 | Generator and stabilizer installation | Systems installation | 1 | Units installed and aligned / units | N | 50 | 40 | Generators landed, stabilizers not yet fitted
5.4 | Piping, HVAC, electrical and cabling | Systems installation | 10 | Pipe spools fitted, cable metres pulled, tested (weighted) | N | 18.2 | 15 | Spool and cable counts, weekly sheet
6.1 | Fairing and exterior paint | Fairing, paint and exterior | 8 | Steps per zone: fairing, primer, filler, topcoat | Y | 0 | 0
6.2 | Exterior outfitting: glazing, teak, rails | Fairing, paint and exterior | 3 | Items fitted / items | N | 0 | 0
7.1 | Interior outfitting | Interior and AV/IT | 12 | Rooms by stage (weighted) | N | 0 | 0
7.2 | AV/IT installation | Interior and AV/IT | 2 | Systems installed / systems | N | 0 | 0
8.2 | Commissioning and harbour acceptance tests | Commissioning, trials and delivery | 3 | Test procedures passed / procedures | Y | 0 | 0
8.3 | Sea trials | Commissioning, trials and delivery | 1 | 0/100 | Y | 0 | 0
8.5 | Punch list close-out, final finish, crew handover | Commissioning, trials and delivery | 2 | Punch items closed / items | Y | 0 | 0
Total
Monthly log (copy the month's totals here; the charts redraw)
Month | Planned (cumulative) | Measured (cumulative) | Index
0 | 0 | 0
1 | 0.6 | 0.6
2 | 1.9 | 1.8
3 | 4.2 | 4.1
4 | 6.8 | 6.9
5 | 11 | 11.1
6 | 15.3 | 15.2
7 | 19.5 | 19.3
8 | 24.1 | 23.8
9 | 29.5 | 28.9
10 | 35 | 34.1
11 | 40.4 | 39.2
12 | 44.1 | 42.6
13 | 49 | 47
14 | 53.8 | 51.2
15 | 56.9
16 | 61.6
17 | 65
18 | 68.5
19 | 71.9
20 | 75.3
21 | 78.8
22 | 82.4
23 | 86
24 | 88
25 | 91.5
26 | 95
27 | 97
28 | 98
29 | 99
30 | 100