## Read me
TPL-SPM-T3 ¦ project2-me.com
T3 Regulatory Applicability Matrix
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
What it does
Records the early rule decisions for a yacht build (use, guests, code, tonnage target, flag, class and notation) and shows which code requirements and certificates follow from them. For each requirement you record who approves or issues it, whether the flag has delegated it to a Recognised Organisation (RO), who owns it on the owner's side and when it was confirmed.
How to use it
1. Fill the project inputs (white cells; hover for a note on each). The gate cells show the code part, the margin to 500 GT and the lines crossed.
2. Read the Applies? column: Yes, No, Near (within the 'Near' margin of a tonnage line) or Check (an input is missing).
3. For every Yes and Near row, fill who approves or surveys, who issues, whether it is delegated, the owner-side person, the date confirmed and the status.
4. Log each early decision in the decision log with options, reasons and evidence.
5. Update the GT estimate each month from the naval architect's figure; Near rows are the ones to watch.
Limits
The rows are a simplified extract from the REG Yacht Code, July 2024 edition (Part A, Part B and Common Annexes L, M, N). They are not a complete list and they do not replace the flag's or the class society's own requirements. Add national requirements of the flag and of the cruising area. Codes and rules change: check the current editions. This workbook is a planning aid, not legal or regulatory advice.
Private use: Part A applies to yachts in commercial use. For a private yacht the gate shows 'Code voluntary', and the rows show what would apply if the code were adopted.
Sheets
Blank: empty inputs, the full requirement list and an empty decision log. Example (YP-48, illustrative): the example yacht at contract signature, Cayman Islands flag and Lloyd's Register class.
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
In the example the RO split is not yet confirmed; 'Confirm' in a cell means the entry is the expected route, to be confirmed in writing. The contract date (4 Jan 2027) is the illustrative date used in the YP-48 schedule; decision dates are left blank because the series does not fix a pre-contract calendar. Load line length is left blank (not yet given by the naval architect), so the sheet tests length overall and asks for confirmation.
White cells are inputs. Grey cells are formulas.

## Blank
TPL-SPM-T3 ¦ project2-me.com
T3 Regulatory Applicability Matrix
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
Project inputs
| Intended use (Private / Charter / Both) | [5 empty] | 24 m load line length test | [5 empty] | Rows Yes
| Length overall (m) | [5 empty] | Code part | [5 empty] | Rows Near
| Load line length (m) | [5 empty] | Code edition | [5 empty] | Rows Check
| Maximum passengers (guests, as the code defines them) | [5 empty] | Margin: target to 500 GT | [5 empty] | Yes/Near rows without status
| Crew (planning figure) | [5 empty] | Margin: estimate to target
| Gross tonnage target | [5 empty] | Margin: estimate to 500 GT
| Gross tonnage, current estimate | [5 empty] | Highest line crossed
| 'Near' margin (GT) | [5 empty] | 500 GT status
| Operates in EU waters? (Yes / No) | [5 empty] | RO split
Building contract date
Flag / register
Class society
Class notation (as confirmed by the society)
RO split confirmed in writing by the flag? (Yes / No)
Applicability matrix
No | Group | Requirement | Basis | Threshold | Reference (REG Yacht Code, July 2024 edition) | Applies? | Certificate / output | Plan approval or survey by | Issued by | Delegated to RO? | Owner-side responsible | Confirmed on | Status | Notes
1 | Scope | REG Yacht Code Part A applies | Use, LL, pax |  | Part A 1.2 |  | REG Yacht Code Certificate
2 | Scope | REG Yacht Code Part B applies instead (13 to 36 passengers) | Passengers | 12 | Part B 1.2 |  | Passenger (Yacht) Ship Safety Certificate and Form P
3 | All Part A | Registry | All |  | Annex M2(1) |  | Certificate of registry
4 | All Part A | Tonnage measurement | All |  | Annex M2(2) |  | International Tonnage Certificate
5 | All Part A | Classification by an RO, built to RO requirements | All |  | Part A Ch 4; Annex M2(4) |  | Certificate of Classification
6 | All Part A | Load line assignment | All |  | Part A Ch 12; Annex M2(5)(6) |  | International Load Line Certificate and conditions of assignment
7 | All Part A | Stability: inclining in presence of the Administration | All |  | Part A 11.9, 11.10 |  | Approved inclining report and stability information
8 | All Part A | Minimum safe manning | All |  | Annex M2(8); Annex G |  | Minimum Safe Manning Document
9 | All Part A | Radio station licence | All |  | Annex M2(11) |  | Ship station radio licence
10 | All Part A | Engine NOx (each engine over 130 kW) | All |  | Annex M2(10) |  | EIAPP certificate and NOx technical file per engine
11 | All Part A | Ballast water management (if water ballast used) | All |  | Annex L5; Annex M2(12) |  | BWM certificate or statement, if applicable
12 | Persons | Sewage pollution prevention (more than 15 persons) | Persons over | 15 | Annex M2(7) |  | Sewage certificate or statement
13 | Persons / GT | Garbage management plan (100 GT or 15 persons) | GT or 15 persons | 100 | Annex L3 |  | Garbage management plan and record book
14 | Below 500 GT | Safety management system to Ch 23A | GT below | 500 | Part A 23A.1 |  | SMS documentation (no ISM certificate)
15 | Below 400 GT | Anti-fouling owner's declaration | GT below | 400 | Annex M2(9) |  | AFS owner's declaration
16 | 200 GT | Crew accommodation to Ch 21B (else 21A) | GT at or above | 200 | Part A Ch 21A / 21B |  | Accommodation plans approved to 21B
17 | 300 GT | Radio to full SOLAS IV cargo ship requirements | GT at or above | 300 | Part A 16.1; Annex M3(1) |  | Safety Radio Certificate and Form R
18 | 300 GT | Wreck removal insurance | GT at or above | 300 | Annex L7; Annex M3(2) |  | Wreck Removal Convention certificate
19 | 400 GT | MARPOL oil pollution prevention | GT at or above | 400 | Annex L3; Annex M4(1) |  | IOPP certificate and record
20 | 400 GT | MARPOL air pollution prevention | GT at or above | 400 | Annex M4(2) |  | IAPP certificate or statement and record
21 | 400 GT | Energy efficiency | GT at or above | 400 | Annex M4(3) |  | International Energy Efficiency certificate or statement
22 | 400 GT | Anti-fouling systems | GT at or above | 400 | Annex L4; Annex M4(4) |  | AFS certificate or statement
23 | 500 GT | 'B' technical chapters: machinery, electrical, steering, bilge | GT at or above | 500 | Part A Ch 7B, 8B, 9B, 10B |  | Design to 'B' chapters
24 | 500 GT | Structural fire protection and fire appliances to 14B / 15B | GT at or above | 500 | Part A Ch 14B, 15B |  | Design to 'B' chapters
25 | 500 GT | SOLAS safety construction | GT at or above | 500 | Annex M5(1) |  | Safety Construction Certificate
26 | 500 GT | SOLAS safety equipment | GT at or above | 500 | Annex M5(2) |  | Safety Equipment Certificate
27 | 500 GT | ISM Code (SOLAS IX) | GT at or above | 500 | Part A 23B.1; Annex M5(3) |  | Safety Management Certificate (and company DOC)
28 | 500 GT | ISPS Code | GT at or above | 500 | Part A 31.1; Annex M5(4) |  | International Ship Security Certificate
29 | 500 GT | Continuous Synopsis Record | GT at or above | 500 | Annex M5(5) |  | CSR file
30 | 500 GT | Maritime Labour Convention certificate | GT at or above | 500 | Annex L8; Annex M5(6) |  | MLC certificate, DMLC Parts I and II
31 | 500 GT + EU | Inventory of Hazardous Materials (EU waters) | GT + EU waters | 500 | Annex L13; Annex M5(7) |  | IHM certificate
32 | 1000 GT | Bunkers Convention insurance | GT at or above | 1000 | Annex L6; Annex M6 |  | Bunkers certificate
33 | Length | Lifeboats (vessels over 85 m) | LL length over | 85 | Part A 13.2 |  | LSA arrangement with lifeboats
34 | Flag / national
35
36
37
38
Decision log
No | Decision |  | Options considered |  |  | Chosen |  | Main reasons |  |  | Decided by | Date | Evidence ref | Status
1 | Intended use
2 | Maximum guest number
3 | Code and edition
4 | GT target and margin rules
5 | Flag / register
6 | Class society
7 | Class notation
8 | RO split and approval routes
Note on D6: Charter or Both = commercial use
Note on D7: For information
Note on D8: Code scope uses load line length
Note on D9: 12 or fewer: Part A
Note on D10: Leave blank until fixed
Note on D11: Design target
Note on D12: Naval architect's latest figure
Note on D13: Rows within this margin of a line show Near
Note on D14: For IHM row
Note on D15: On or after 1 Jul 2024: July 2024 edition in full
Note on D18: Confirm against the current rules edition
Note on D19: Needed before the drawing register is issued

## Example (YP-48)
TPL-SPM-T3 ¦ project2-me.com
T3 Regulatory Applicability Matrix
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects ¦ Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Project inputs
| Intended use (Private / Charter / Both) |  | Both |  |  |  | 24 m load line length test | [5 empty] | Rows Yes
| Length overall (m) |  | 48 |  |  |  | Code part | [5 empty] | Rows Near
| Load line length (m) | [5 empty] | Code edition | [5 empty] | Rows Check
| Maximum passengers (guests, as the code defines them) |  | 12 |  |  |  | Margin: target to 500 GT | [5 empty] | Yes/Near rows without status
| Crew (planning figure) | [5 empty] | Margin: estimate to target
| Gross tonnage target |  | 499 |  |  |  | Margin: estimate to 500 GT
| Gross tonnage, current estimate |  | 488 |  |  |  | Highest line crossed
| 'Near' margin (GT) |  | 15 |  |  |  | 500 GT status
| Operates in EU waters? (Yes / No) |  | Yes |  |  |  | RO split
| Building contract date |  | 2027-01-04
| Flag / register |  | Cayman Islands (CISR), REG Category 1
| Class society |  | Lloyd's Register (SSC Rules)
| Class notation (as confirmed by the society) |  | ✠100A1 SSC Yacht Mono G6, ✠LMC, UMS (from July 2020 SSC text; LR to confirm against July 2026 edition)
| RO split confirmed in writing by the flag? (Yes / No) |  | No
Applicability matrix
No | Group | Requirement | Basis | Threshold | Reference (REG Yacht Code, July 2024 edition) | Applies? | Certificate / output | Plan approval or survey by | Issued by | Delegated to RO? | Owner-side responsible | Confirmed on | Status | Notes
1 | Scope | REG Yacht Code Part A applies | Use, LL, pax |  | Part A 1.2 |  | REG Yacht Code Certificate | CISR surveyors (code compliance) | CISR | Confirm | Owner's rep |  | Confirm in writing | Charter use: Part A applies by law
2 | Scope | REG Yacht Code Part B applies instead (13 to 36 passengers) | Passengers | 12 | Part B 1.2 |  | Passenger (Yacht) Ship Safety Certificate and Form P | [5 empty] | Not applicable | 12 guests. A 13th guest moves the yacht to Part B
3 | All Part A | Registry | All |  | Annex M2(1) |  | Certificate of registry |  | CISR | No | Owner |  | Open | Registration before delivery; ownership documents from the Owner's side
4 | All Part A | Tonnage measurement | All |  | Annex M2(2) |  | International Tonnage Certificate | Surveyor per flag arrangement | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
5 | All Part A | Classification by an RO, built to RO requirements | All |  | Part A Ch 4; Annex M2(4) |  | Certificate of Classification | LR (class) | LR | n/a | Owner's rep |  | Confirmed | Class named in the contract; notation to be confirmed in writing by LR
6 | All Part A | Load line assignment | All |  | Part A Ch 12; Annex M2(5)(6) |  | International Load Line Certificate and conditions of assignment | RO if delegated | CISR or LR as RO | Confirm | Owner's rep |  | Confirm in writing | Load line is a typical delegated item; check the RO agreement
7 | All Part A | Stability: inclining in presence of the Administration | All |  | Part A 11.9, 11.10 |  | Approved inclining report and stability information | Administration present at inclining | CISR | Confirm | Owner's rep + NA |  | Open | LR 'Yacht' notation also needs stability shown to meet flag requirements
8 | All Part A | Minimum safe manning | All |  | Annex M2(8); Annex G |  | Minimum Safe Manning Document |  | CISR | No | Owner / captain |  | Open | Crew number still open
9 | All Part A | Radio station licence | All |  | Annex M2(11) |  | Ship station radio licence |  | CISR | No | Owner's rep |  | Open | Apply before trials
10 | All Part A | Engine NOx (each engine over 130 kW) | All |  | Annex M2(10) |  | EIAPP certificate and NOx technical file per engine | Engine maker / RO | Per flag arrangement | Confirm | Yard |  | Open | One per engine over 130 kW; Yard collects from engine makers
11 | All Part A | Ballast water management (if water ballast used) | All |  | Annex L5; Annex M2(12) |  | BWM certificate or statement, if applicable |  |  |  | Yard |  | Open | Confirm whether water ballast is used
12 | Persons | Sewage pollution prevention (more than 15 persons) | Persons over | 15 | Annex M2(7) |  | Sewage certificate or statement |  |  |  | Owner's rep |  | Open | Depends on crew number: 12 guests + crew
13 | Persons / GT | Garbage management plan (100 GT or 15 persons) | GT or 15 persons | 100 | Annex L3 |  | Garbage management plan and record book | Per RO split |  | Confirm | Owner / captain |  | Open | Applies: YP-48 is above 100 GT
14 | Below 500 GT | Safety management system to Ch 23A | GT below | 500 | Part A 23A.1 |  | SMS documentation (no ISM certificate) | CISR | CISR | Confirm | Owner / manager |  | Open | Owner-side duty, not the Yard's
15 | Below 400 GT | Anti-fouling owner's declaration | GT below | 400 | Annex M2(9) |  | AFS owner's declaration
16 | 200 GT | Crew accommodation to Ch 21B (else 21A) | GT at or above | 200 | Part A Ch 21A / 21B |  | Accommodation plans approved to 21B | Per RO split |  | Confirm | Owner's rep |  | Confirm in writing | YP-48 is above 200 GT
17 | 300 GT | Radio to full SOLAS IV cargo ship requirements | GT at or above | 300 | Part A 16.1; Annex M3(1) |  | Safety Radio Certificate and Form R | Per RO split | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
18 | 300 GT | Wreck removal insurance | GT at or above | 300 | Annex L7; Annex M3(2) |  | Wreck Removal Convention certificate |  | CISR | No | Owner |  | Open | Insurance from the Owner's side
19 | 400 GT | MARPOL oil pollution prevention | GT at or above | 400 | Annex L3; Annex M4(1) |  | IOPP certificate and record | Per RO split | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
20 | 400 GT | MARPOL air pollution prevention | GT at or above | 400 | Annex M4(2) |  | IAPP certificate or statement and record | Per RO split | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
21 | 400 GT | Energy efficiency | GT at or above | 400 | Annex M4(3) |  | International Energy Efficiency certificate or statement | Per RO split | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
22 | 400 GT | Anti-fouling systems | GT at or above | 400 | Annex L4; Annex M4(4) |  | AFS certificate or statement | Per RO split | CISR or RO | Confirm | Owner's rep |  | Confirm in writing
23 | 500 GT | 'B' technical chapters: machinery, electrical, steering, bilge | GT at or above | 500 | Part A Ch 7B, 8B, 9B, 10B |  | Design to 'B' chapters |  |  |  | Naval architect |  | Open | Near: design stays on the 'A' chapters only while under 500 GT
24 | 500 GT | Structural fire protection and fire appliances to 14B / 15B | GT at or above | 500 | Part A Ch 14B, 15B |  | Design to 'B' chapters |  |  |  | Naval architect |  | Open | Near: 14B would reach into the interior design
25 | 500 GT | SOLAS safety construction | GT at or above | 500 | Annex M5(1) |  | Safety Construction Certificate |  |  |  | Owner's rep |  | Open | Near: watch the GT margin
26 | 500 GT | SOLAS safety equipment | GT at or above | 500 | Annex M5(2) |  | Safety Equipment Certificate |  |  |  | Owner's rep |  | Open | Near
27 | 500 GT | ISM Code (SOLAS IX) | GT at or above | 500 | Part A 23B.1; Annex M5(3) |  | Safety Management Certificate (and company DOC) |  |  |  | Owner |  | Open | Near: would need a company ashore
28 | 500 GT | ISPS Code | GT at or above | 500 | Part A 31.1; Annex M5(4) |  | International Ship Security Certificate |  |  |  | Owner |  | Open | Near
29 | 500 GT | Continuous Synopsis Record | GT at or above | 500 | Annex M5(5) |  | CSR file |  |  |  | Owner's rep |  | Open | Near
30 | 500 GT | Maritime Labour Convention certificate | GT at or above | 500 | Annex L8; Annex M5(6) |  | MLC certificate, DMLC Parts I and II |  |  |  | Owner / captain |  | Open | Near
31 | 500 GT + EU | Inventory of Hazardous Materials (EU waters) | GT + EU waters | 500 | Annex L13; Annex M5(7) |  | IHM certificate |  |  |  | Owner's rep |  | Open | Near; EU waters = Yes in inputs
32 | 1000 GT | Bunkers Convention insurance | GT at or above | 1000 | Annex L6; Annex M6 |  | Bunkers certificate
33 | Length | Lifeboats (vessels over 85 m) | LL length over | 85 | Part A 13.2 |  | LSA arrangement with lifeboats
34 | Flag / national
35
36
37
38
Decision log
No | Decision |  | Options considered |  |  | Chosen |  | Main reasons |  |  | Decided by | Date | Evidence ref | Status
1 | Intended use |  | Private only / private and charter |  |  | Private and charter |  | Owner intends to charter; charter is commercial use |  |  | Owner |  | Design brief rev 0 | Decided
2 | Maximum guest number |  | 12 / more than 12 |  |  | 12 |  | Stays in Part A; more than 12 brings Part B |  |  | Owner |  | Design brief rev 0 | Decided
3 | Code and edition |  | REG Yacht Code Part A |  |  | Part A, July 2024 edition |  | Contract after 1 Jul 2024 (Part A 1.6) |  |  | Owner (rep advises) |  | Outline spec, general section | Decided
4 | GT target and margin rules |  | Under 500 GT / 500 GT and over |  |  | 499 GT target; warn below 3 GT margin |  | Avoid 'B' chapters, ISM, ISPS, 500 GT certificates |  |  | Owner (NA estimates) |  | Tonnage estimate rev 0 | Decided
5 | Flag / register |  | Red Ensign Category 1 registers |  |  | Cayman Islands |  | REG code applies; registry offers plan approval and construction supervision; LR on its RO list |  |  | Owner |  | Decision memo (illustrative) | Decided
6 | Class society |  | IACS societies on the flag's RO list |  |  | Lloyd's Register |  | SSC Rules with Yacht notation; on CISR RO list |  |  | Owner |  | Decision memo; contract clause | Decided
7 | Class notation |  |  |  |  | ✠100A1 SSC Yacht Mono G6, ✠LMC, UMS |  | Unrestricted service; UMS is the Owner's choice |  |  | Owner with Yard |  | LR written confirmation (pending) | Proposed
8 | RO split and approval routes | [6 empty] | To be confirmed with CISR before the drawing register is issued |  |  | Owner's rep and Yard |  |  | Open
Note on D6: Charter or Both = commercial use
Note on D7: For information
Note on D8: Code scope uses load line length
Note on D9: 12 or fewer: Part A
Note on D10: Leave blank until fixed
Note on D11: Design target
Note on D12: Naval architect's latest figure
Note on D13: Rows within this margin of a line show Near
Note on D14: For IHM row
Note on D15: On or after 1 Jul 2024: July 2024 edition in full
Note on D18: Confirm against the current rules edition
Note on D19: Needed before the drawing register is issued