## Read Me
TPL-SPM-T11 ¦ project2-me.com
Decision and Action Log (T11)
How to use this workbook: a decision log, a monthly review agenda and an action list for the owner's side of a yacht build.
What it is
An owner-side workbook for the questions a yacht build needs answered and the actions that lead to the answers. It sits beside the change log (T9), the drawing approval register (T7) and the weekly owner report (T10); it does not replace them.
Sheets
Decision Log - Blank / Decision Log - Example: one line per question for the Owner (or for the owner's rep under the delegation letter).
Review & Actions - Blank / Review & Actions - Example: a monthly owner review agenda with total minutes, and the running action list.
Decision log: how to use it
Set the as-at date at the top (today, or the date of the review). All counters and flags work from it.
Enter each question when it is raised, phrased so it can be answered (for example 'sample A or sample B'). Start the log from the contract's list of open items: everything described as to Owner's choice, to be selected or as an allowance.
Needed by: the planned start of the schedule activity that consumes the answer, minus the Yard's lead time after the decision. Deciding by this date uses no float.
Last responsible date: the same, worked from the activity's late start (planned start plus float), or an earlier limit such as the validity of the Yard's offer. Deciding later than this moves delivery.
Affects schedule if late: Yes when the consuming activity leads to delivery or a contractual milestone.
Statuses: Open, Deferred (still counted as open), Decided (confirmed in writing by the authorised person), Closed (the Yard has received the instruction), Withdrawn. Never delete a line; a reversed decision gets a new line.
Grey columns are formulas: days to needed-by, days decided late, days to the last responsible date and a flag (PAST LAST RESPONSIBLE DATE, OVERDUE, DUE WITHIN 7 DAYS, Open, Done). Do not type over them.
Counters
Open decisions; overdue (open, past needed-by); open and affecting the schedule; overdue and affecting the schedule; due in the next 14 days; past the last responsible date; number of decisions made after their needed-by date and the total days late.
Review & Actions
Fill the meeting details and the agenda before the meeting and send them with the decision papers. The total minutes are summed. Actions: one line per action with a named owner and a due date; the flag shows OVERDUE and Due soon from the as-at date.
Example data
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
The examples show the owner's side of the fictional YP-48 on the morning of the month-14 owner review (8 March 2028), consistent with the week 61 report in lesson L10. All dates and durations are illustrative teaching values.
Limits
Who may decide, and in which channel a decision counts as written, is set by your contract and the Owner's delegation letter. This workbook records decisions; it does not make any of them binding.

## Decision Log - Blank
TPL-SPM-T11 ¦ project2-me.com
Decision and Action Log (T11): Decision Log
Blank log. The as-at date defaults to today; overwrite it with the review date if you prefer.
As-at date |  |  |  | Enter today's date or the date of the review. Grey columns are formulas; do not type over them. 'Open' counts include 'Deferred'.
Open decisions |  |  | Overdue (open, past needed-by) |  |  | Open, affecting schedule |  |  | Overdue and affecting schedule
Due in the next 14 days |  |  | Past last responsible date |  |  | Decided after needed-by |  |  | Total days decided late
One line per question that needs an answer from the Owner (or from the owner's rep under the delegation letter). Needed-by: planned start of the consuming activity minus the Yard's lead time after the decision. Last responsible date: the same from the late start, or an earlier limit such as an offer's validity.
Ref | Date raised | Question (answerable as asked) | Options and recommendation | Who decides | Consulted before deciding | Consuming schedule activity | Needed by (no float used) | Last responsible date (float used) | Affects schedule if late? | Status | Date decided | Decision and where the written confirmation is filed | Link (CR, drawing, sample) | Notes | Days to needed-by | Days decided late | Days to last responsible date | Flag

## Decision Log - Example
TPL-SPM-T11 ¦ project2-me.com
Decision and Action Log (T11): Decision Log
Example: YP-48 as at the month-14 owner review, 8 March 2028. Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
As-at date |  | 2028-03-08 |  | Enter today's date or the date of the review. Grey columns are formulas; do not type over them. 'Open' counts include 'Deferred'.
Open decisions |  |  | Overdue (open, past needed-by) |  |  | Open, affecting schedule |  |  | Overdue and affecting schedule
Due in the next 14 days |  |  | Past last responsible date |  |  | Decided after needed-by |  |  | Total days decided late
One line per question that needs an answer from the Owner (or from the owner's rep under the delegation letter). Needed-by: planned start of the consuming activity minus the Yard's lead time after the decision. Last responsible date: the same from the late start, or an earlier limit such as an offer's validity.
Ref | Date raised | Question (answerable as asked) | Options and recommendation | Who decides | Consulted before deciding | Consuming schedule activity | Needed by (no float used) | Last responsible date (float used) | Affects schedule if late? | Status | Date decided | Decision and where the written confirmation is filed | Link (CR, drawing, sample) | Notes | Days to needed-by | Days decided late | Days to last responsible date | Flag
D-01 | 2027-01-04 | Approve the RACI matrix and issue the delegation letter | As drafted / with changes | Owner | Owner's rep, family office | 1.1 Contract and project milestones | 2027-01-15 | 2027-01-15 | No | Closed | 2027-01-14 | Approved as drafted; letter copied to the Yard | T2 | Kick-off
D-02 | 2027-01-18 | Stabilizer system: option A or option B from the makers list | A / B (weight, noise and price from the Yard's comparison) | Owner | Owner's rep, captain, naval architect | 3.3 Stabilizers: order to delivery | 2027-02-26 | 2027-03-26 | Yes | Closed | 2027-03-03 | Option A | Makers list | Decided 5 days after the needed-by date; absorbed in the stabilizer float
D-03 | 2027-04-05 | CR-01: enclosed gym on the bridge deck aft | Accept VO-01 / reject | Owner | Owner's rep, Design Studio, naval architect | 2.1 Basic design and plan approval | 2027-05-14 | 2027-06-04 | Yes | Closed | 2027-05-10 | VO-01 signed: 0.40, 0 days, +4.7 GT | CR-01 / VO-01 | Mirrored from the change log (T9)
D-04 | 2027-06-07 | Design freeze: sign the GA and interior layout | Sign / sign with listed exceptions | Owner | Owner's rep, captain, Design Studio, naval architect | 2.2 Design freeze (GA and interior layout) | 2027-08-04 | 2027-08-04 | Yes | Closed | 2027-08-02 | Signed without exceptions | T7 | Owner decision milestone in L8
D-05 | 2027-09-06 | CR-02: wheelhouse deckhead raised 150 mm | Accept VO-02 / reject | Owner | Owner's rep, naval architect | 4.4 Aluminium superstructure | 2027-09-29 | 2027-10-13 | Yes | Closed | 2027-09-24 | VO-02 signed: 0.55, 0 days, +1.6 GT | CR-02 / VO-02 | Mirrored from T9
D-06 | 2027-09-13 | Interior material palette: timber species, stone families, metal finish | Design Studio palettes 1 to 3 | Owner | Owner's rep, Design Studio, naval architect (weight) | 2.4 Interior detail design and sample approval | 2027-10-29 | 2027-11-26 | Yes | Closed | 2027-10-27 | Palette 2; stone weight checked by the naval architect | Sample register
D-07 | 2027-10-11 | CR-03: move the engine room switch panel to the forward bulkhead | Accept VO-03 / reject | Owner's rep | Captain | 5.4 Piping, HVAC, electrical and cabling | 2027-10-29 | 2027-12-17 | No | Closed | 2027-10-25 | VO-03 signed by the rep: 0.06, 0 days | CR-03 / VO-03 | Inside the delegation letter
D-08 | 2027-10-18 | Limousine tender: model and size | Three shortlisted tenders | Owner | Captain, Owner's rep | Owner's supply | 2027-11-30 | 2027-12-31 | No | Closed | 2027-11-19 | Largest of the three | CR-06 | Garage interface not checked before the choice; led to CR-06 (D-16)
D-09 | 2027-12-06 | CR-04: sky lounge cinema system | Accept one merged VO / reject | Owner | Owner's rep, Design Studio | 7.2 AV/IT installation | 2028-01-14 | 2028-02-11 | Yes | Closed | 2028-01-10 | VO-04 signed: 0.40, 0 days | CR-04 / VO-04 | Mirrored from T9
D-10 | 2028-01-10 | Guest cabin full-scale mock-up: release joinery production | Release / release with comments / rework mock-up | Owner | Owner's rep (technical), captain, Design Studio | 3.5 Interior joinery package | 2028-01-28 | 2028-02-25 | Yes | Closed | 2028-01-26 | Released with 3 comments (see D-12) | Sample register | Owner visit to the Yard
D-11 | 2027-12-13 | AV/IT concept: level of equipment per space | Design Studio concept levels 1 to 3 | Owner | Owner's rep, captain, AV/IT designer | 2.4 Interior detail design | 2028-01-14 | 2028-02-11 | Yes | Closed | 2028-01-12 | Level 2, cinema per D-09 | AV/IT spec | Feeds D-15
D-12 | 2028-02-14 | Guest cabin mock-up comments: accept the Yard's revised joinery details | Accept / return with comments | Owner's rep | Captain, Design Studio | 3.5 Interior joinery package | 2028-03-03 | 2028-04-07 | Yes | Open |  |  | D-10 | Waiting for the captain's comment on locker depth (action A-38)
D-13 | 2028-02-28 | CR-05: enclosed sun-deck bar | Proceed to pricing / reject | Owner | Owner's rep, naval architect | 4.4 Aluminium superstructure | 2028-03-03 | 2028-03-03 | No | Closed | 2028-03-01 | Rejected: estimate would pass 500 GT | CR-05 | Mirrored from T9; never priced
D-14 | 2028-02-18 | Master bathroom stone: sample A or sample B | A / B (weights in the sample register) | Owner | Design Studio, naval architect (weight) | 7.1 Interior outfitting (master bathroom) | 2028-03-10 | 2028-04-07 | Yes | Open |  |  | Sample register | Recommendation: B (lighter, same lead time)
D-15 | 2028-02-25 | Sign off the AV/IT specification rev C so the order can be placed | Sign rev C / sign with the two open comments | Owner | Owner's rep, captain, Design Studio | 3.6 AV/IT and navigation: order to delivery | 2028-03-17 | 2028-04-14 | Yes | Open |  |  | D-11 | Recommendation: sign rev C, handle comments as a later change
D-16 | 2028-02-28 | CR-06: larger hydraulic tender garage door | Accept VO-06 / reject | Owner | Owner's rep, captain, naval architect | 5.5 Hot work complete | 2028-03-17 | 2028-04-10 | Yes | Open |  |  | CR-06 | Yard price expected week 62; weight +0.3 of 0.6 margin
D-17 | 2028-03-08 | Hull colour and topcoat finish: approve sample panels | Two colour panels, gloss levels | Owner | Design Studio, captain | 6.1 Fairing and exterior paint | 2028-06-30 | 2028-07-28 | Yes | Open |  |  |  | New at the month-14 review
D-18 | 2028-03-08 | Loose furniture, guest areas: final selection | Design Studio schedule rev A | Owner | Design Studio, naval architect (weight) | 7.1 Interior outfitting | 2028-08-31 | 2028-09-29 | No | Open |  |  |  | New at the month-14 review

## Review & Actions - Blank
TPL-SPM-T11 ¦ project2-me.com
Decision and Action Log (T11): Review Agenda and Action List
Blank monthly review agenda and action list. The as-at date defaults to today.
As-at date
Meeting
Date
Place
Chair / minutes
Attendees
Next review
Agenda
Minutes | Item |  |  | Lead | Input |  | Expected outcome |  | Decision / action refs | Outcome (fill in the meeting)
Total minutes
Action list
Open actions |  |  | Overdue actions |  | Due in next 7 days |  |  | Max days overdue
Ref | Date raised | Source (meeting) | Action | Owner (person / party) | Due | Status | Date closed | Linked decision | Days overdue | Flag

## Review & Actions - Example
TPL-SPM-T11 ¦ project2-me.com
Decision and Action Log (T11): Review Agenda and Action List
Example: YP-48 month-14 owner review, 8 March 2028. Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
As-at date |  | 2028-03-08
Meeting |  | Monthly owner review, month 14
Date |  | 2028-03-08
Place |  | Video; owner's rep and Yard PM at the Yard
Chair / minutes |  | Owner's rep / owner's rep
Attendees |  | Owner, family office director, build captain, owner's rep; Yard PM for the Yard session; Design Studio for D-17 and D-18
Next review |  | 2028-04-05
Agenda
Minutes | Item |  |  | Lead | Input |  | Expected outcome |  | Decision / action refs | Outcome (fill in the meeting)
5 | Actions from the month-13 review |  |  | Owner's rep | Action list below |  | Open actions re-dated or closed |  | A-31 to A-39
10 | Where we stand: forecast against the contract dates |  |  | Owner's rep | Week 61 report (T10), month-14 measurement |  | Owner agrees the forecast and the red trigger at the week 63 superstructure checkpoint
25 | Decisions due now |  |  | Owner's rep | Decision papers, both stone samples, CR-06 status |  | D-14 and D-15 decided; D-16: decision date before 13 March or a named delegate |  | D-14, D-15, D-16
10 | Decisions due in the next 90 days |  |  | Owner's rep, Design Studio | Decision log |  | Dates agreed; D-17 sample panels booked |  | D-17, D-18
10 | Changes and money |  |  | Owner's rep | Change log summary (T9) |  | Owner sees signed total and pending exposure |  | CR-06
5 | Owner's diary: travel 13 to 24 March |  |  | Family office | Action A-33 |  | Written confirmation of who confirms Owner decisions during the travel |  | A-33
15 | Yard session: recovery plan and AV/IT order timing |  |  | Yard PM | Recovery plan, section count |  | Yard commitments recorded as actions |  | A-31
5 | Read back decisions and actions |  |  | Owner's rep | Notes |  | Everyone hears the same list before leaving
Total minutes
Action list
Open actions |  |  | Overdue actions |  | Due in next 7 days |  |  | Max days overdue
Ref | Date raised | Source (meeting) | Action | Owner (person / party) | Due | Status | Date closed | Linked decision | Days overdue | Flag
A-31 | 2028-02-09 | Month-13 owner review | Send the superstructure recovery plan: names, second shift, dated section list | Yard PM | 2028-02-25 | Closed | 2028-02-24
A-32 | 2028-02-09 | Month-13 owner review | Send the D-14 decision paper with photos of both samples in daylight and under the yacht's lighting | Owner's rep | 2028-02-23 | Closed | 2028-02-22 | D-14
A-33 | 2028-02-09 | Month-13 owner review | Confirm in writing who may confirm Owner decisions during the Owner's travel, 13 to 24 March | Family office | 2028-03-08 | Open |  | D-15, D-16
A-34 | 2028-02-15 | Weekly site meeting wk 59 | Book the joint inspection for milestone 3 | Yard PM | 2028-03-03 | Closed | 2028-03-01 | MS3
A-35 | 2028-02-22 | Weekly site meeting wk 60 | Naval architect's weight check for CR-06 | Yard PM | 2028-03-10 | Open |  | D-16
A-36 | 2028-02-28 | Weekly decision call | List the two open comments on AV/IT specification rev C with a cost view | Design Studio | 2028-03-06 | Open |  | D-15
A-37 | 2028-02-29 | Weekly site meeting wk 61 | Price and time for CR-06 (request for proposal sent) | Yard PM | 2028-03-10 | Open |  | D-16
A-38 | 2028-02-15 | Weekly site meeting wk 59 | Comment on guest cabin locker depth in the Yard's revised details | Captain | 2028-03-01 | Open |  | D-12
A-39 | 2028-02-29 | Weekly site meeting wk 61 | Ship stone samples A and B to the Owner's office for viewing | Owner's rep | 2028-03-03 | Closed | 2028-03-02 | D-14