## Read Me
TPL-SPM-T12 ¦ project2-me.com
Owner Budget Tracker and Risk Register (T12)
How to use this workbook
What it is
An owner-side budget and risk register for a yacht newbuild. It tracks everything the Owner pays for, not only the contract price: variation orders, allowance over- or underspend, owner-furnished items, the owner's team and advisers, registration, insurance, financing, crew before delivery and delivery costs, plus contingency and a management reserve held by the Owner.
Sheets
Budget - Blank / Budget - Example YP-48: one row per budget line. Enter the budget at signing, committed, paid and forecast at completion. Transfers from contingency and Owner-approved budget changes are entered in the two logs under the table and pulled into each line by its exact name (use the drop-down).
Risks - Blank / Risks - Example YP-48: one row per risk. Enter probability %, cost impact (index or currency) and time impact in weeks. The sheet scores P and I, multiplies them, sets the level and calculates the expected value. Mark Y if the contingency is meant to cover the risk.
Rules used by the formulas
Current budget = budget at signing + transfers from contingency + Owner-approved budget changes. Variance = current budget - forecast at completion (negative means forecast over budget). Contingency remaining = contingency at signing - transfers. Contingency after forecast = remaining + total variance. Coverage = contingency after forecast / expected value of the open risks covered by contingency (below 1.0 is flagged 'Short', below 1.2 'Thin'; set your own thresholds). Currency exposure = unhedged payments still to pay x the move you test.
Contingency is for risks in the register. New scope the Owner chooses is a budget change, not a contingency draw. The management reserve is released only by the Owner, for something no one had listed.
Limits
One currency or index per workbook; no automatic exchange-rate conversion. Formulas cover 25 budget lines, 30 transfers, 15 budget changes and 40 risks. Expected values add up risks as if they were independent; risks that share a cause (for example several that all move the delivery date) can arrive together.
Not financial, tax, insurance or legal advice. Tax, duties, insurance cover and hedging are decisions for the Owner with qualified advisers.
Example data
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described. All money is an index where the contract price is 100. The figures are illustrative, not a benchmark and not a guide to what these items cost on a real yacht.

## Budget - Blank
TPL-SPM-T12 ¦ project2-me.com
Owner Budget Tracker and Risk Register (T12): Owner Budget
Blank. Index or currency; enter your own lines.
| As at (date) |  |  | Owner budget at signing (with reserves)
| Contingency at signing |  |  | Current budget, lines
| Management reserve at signing |  |  | Forecast at completion, lines
| Management reserve used |  |  | Contingency drawn
| Unhedged contract payments still to pay |  |  | Contingency remaining
| Currency sensitivity (move tested) |  |  | Contingency after forecast variance
Owner budget now (with reserves)
Risk exposure (expected value)
Coverage (contingency / exposure)
Coverage check
Currency exposure (move x unhedged)
Currency exposure vs contingency left
Index: contract price = 100 (or your currency). White cells are inputs; grey cells are formulas. Not financial, tax or legal advice.
Budget lines
No | Group | Budget line | Budget at signing | Transfers from contingency | Owner-approved budget changes | Current budget | Committed | Paid to date | Forecast at completion | Variance (current - forecast) | % committed | Flag | Notes
1 | Contract with the Yard | Contract price
2 | Contract with the Yard | Owner changes (variation orders)
3 | Contract with the Yard | Allowance reconciliation (over / under the contract allowances)
4 | Owner-furnished items | Tenders and water toys
5 | Owner-furnished items | Art and installation support
6 | Owner-furnished items | Loose inventory
7 | Owner's team and advisers | Owner's representative and site team
8 | Owner's team and advisers | Designers after signature
9 | Owner's team and advisers | Legal, tax and insurance advisers
10 | Owner's team and advisers | Independent specialists
11 | Registration, insurance and finance | Registration and flag or class items outside the contract
12 | Registration, insurance and finance | Insurance
13 | Registration, insurance and finance | Financing and bank charges
14 | Crew and entry into service | Crew before delivery
15 | Crew and entry into service | Delivery and entry into service
Total, budget lines
Contract price and variation orders are in the lines; contingency and management reserve are held below the line and shown in the summary above.
Contingency transfers (risk events and agreed responses; the total budget does not change)
No | Date | Budget line (exact name) | Amount | Risk ID | Reason | [7 empty] | Approved by
Owner-approved budget changes (new scope the Owner chose; raises the total budget)
No | Date | Budget line (exact name) | Amount |  | Reason | [7 empty] | Approved by

## Budget - Example YP-48
TPL-SPM-T12 ¦ project2-me.com
Owner Budget Tracker and Risk Register (T12): Owner Budget
Example: YP-48 at month 15 (as at 2028-04-03). Illustrative, not a benchmark. Index: contract price = 100.
| As at (date) | 2028-04-03 |  | Owner budget at signing (with reserves)
| Contingency at signing | 3 |  | Current budget, lines
| Management reserve at signing | 2 |  | Forecast at completion, lines
| Management reserve used | 0 |  | Contingency drawn
| Unhedged contract payments still to pay | 61.01 |  | Contingency remaining
| Currency sensitivity (move tested) | 5% |  | Contingency after forecast variance
Owner budget now (with reserves)
Risk exposure (expected value)
Coverage (contingency / exposure)
Coverage check
Currency exposure (move x unhedged)
Currency exposure vs contingency left
Index: contract price = 100 (or your currency). White cells are inputs; grey cells are formulas. Not financial, tax or legal advice.
Budget lines
No | Group | Budget line | Budget at signing | Transfers from contingency | Owner-approved budget changes | Current budget | Committed | Paid to date | Forecast at completion | Variance (current - forecast) | % committed | Flag | Notes
1 | Contract with the Yard | Contract price (includes AV/IT and loose furniture allowances, class and flag approval fees, trials) | 100 |  |  |  | 100 | 25 | 100 |  |  |  | Milestones 1-2 paid; milestone 3 certified, payment due
2 | Contract with the Yard | Owner changes (variation orders) | 2 |  |  |  | 1.41 | 0.4 | 2.16 |  |  |  | Signed 1.41; pending 0.75 at the Yard's figures (L9 log)
3 | Contract with the Yard | Allowance reconciliation (over / under the contract allowances) | 0 |  |  |  | 0 | 0 | 0.3 |  |  |  | AV/IT: Yard's budget quote 0.30 above the 3.50 allowance (CD-02)
4 | Owner-furnished items | Tenders and water toys | 2.2 |  |  |  | 1.9 | 0.6 | 2.65 |  |  |  | Larger limo tender chosen after signing: budget change BC-01
5 | Owner-furnished items | Art and installation support | 0.8 |  |  |  | 0.1 | 0.1 | 0.8 |  |  |  | Art adviser engaged; selection not started
6 | Owner-furnished items | Loose inventory (linen, tableware, galley small items, uniforms) | 0.6 |  |  |  | 0 | 0 | 0.6 |  |  |  | Orders planned from month 24
7 | Owner's team and advisers | Owner's representative and site team | 2.4 |  |  |  | 2.5 | 1.2 | 2.5 |  |  |  | Extra inspector for the second shift (CD-03)
8 | Owner's team and advisers | Design Studio after signature | 1.6 |  |  |  | 1.6 | 0.9 | 1.6 |  |  |  | Fixed fee plus site visits
9 | Owner's team and advisers | Legal, tax and insurance advisers | 0.6 |  |  |  | 0.4 | 0.3 | 0.6
10 | Owner's team and advisers | Independent specialists (noise and vibration, paint inspection) | 0.5 |  |  |  | 0.2 | 0.1 | 0.5 |  |  |  | N&V consultant engaged after contract finding F-09
11 | Registration, insurance and finance | Registration and flag or class items outside the contract | 0.2 |  |  |  | 0 | 0 | 0.2 |  |  |  | Contract includes class and flag approval fees
12 | Registration, insurance and finance | Insurance: owner items on site; hull and machinery and P&I from delivery | 0.9 |  |  |  | 0.05 | 0.05 | 0.9 |  |  |  | First annual premiums fall due at delivery
13 | Registration, insurance and finance | Financing and bank charges | 0.3 |  |  |  | 0.1 | 0.1 | 0.3 |  |  |  | Includes the forward contract for milestone 3
14 | Crew and entry into service | Crew before delivery | 1.8 |  |  |  | 0.3 | 0.15 | 1.95 |  |  |  | Captain joined three months earlier than planned (CD-01)
15 | Crew and entry into service | Delivery and entry into service | 1.2 |  |  |  | 0 | 0 | 1.2 |  |  |  | Delivery trip, fuel, stores, provisions, management set-up
Total, budget lines
Contract price and variation orders are in the lines; contingency and management reserve are held below the line and shown in the summary above.
Contingency transfers (risk events and agreed responses; the total budget does not change)
No | Date | Budget line (exact name) | Amount | Risk ID | Reason | [7 empty] | Approved by
CD-01 | 2027-10-04 | Crew before delivery | 0.15 | R-02 | Captain hired three months early to speed up interior and AV/IT decisions | [7 empty] | Owner
CD-02 | 2028-02-12 | Allowance reconciliation (over / under the contract allowances) | 0.3 | R-09 | Yard's budget quote for the draft AV/IT specification is 0.30 above the allowance | [7 empty] | Owner
CD-03 | 2028-03-06 | Owner's representative and site team | 0.1 | R-01 | Additional inspector while the Yard runs a second shift on the superstructure | [7 empty] | Owner
Owner-approved budget changes (new scope the Owner chose; raises the total budget)
No | Date | Budget line (exact name) | Amount |  | Reason | [7 empty] | Approved by
BC-01 | 2028-03-13 | Tenders and water toys | 0.45 |  | Owner chose a larger limo tender; linked to CR-06 (tender garage door) | [7 empty] | Owner
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
All figures are illustrative index values, not a benchmark and not a guide to what these items cost. Variation orders match the T9 log at month 15 (signed 1.41, pending 0.75).

## Risks - Blank
TPL-SPM-T12 ¦ project2-me.com
Owner Budget Tracker and Risk Register (T12): Risk Register
Blank. Scales and bands in the key; change them before the first review if needed.
| As at (date) |  |  | Probability score: 1 = up to 10%, 2 = 11-30%, 3 = 31-50%, 4 = 51-70%, 5 = over 70%.
| Risks not closed |  |  | Impact score, the higher of cost and time. Cost (index): 1 under 0.1, 2 from 0.1, 3 from 0.3, 4 from 0.6, 5 from 1.2. Time: 1 under 1 week, 2 up to 2 weeks, 3 up to 4 weeks, 4 up to 8 weeks, 5 over 8 weeks.
| Review cycle |  |  | Level: Low 1-6, Medium 7-12, High 13-19, Critical 20-25 (same bands as the site's Shipyard Risk Register Template).
| High or Critical, not closed |  |  | Set your own scales before the first review and keep them for the whole project. Not financial or legal advice.
Expected value in contingency
Expected value outside contingency (e.g. currency)
Largest single cost impact
Risk ID | Risk | Category | Cause / trigger | Probability % | P (1-5) | Cost impact if it occurs (index) | Time impact (weeks) | I (1-5) | Score P x I | Level | Expected value (P% x cost) | Covered by contingency? (Y/N) | Expected value in contingency | Risk owner (a person) | Response | Status | Last reviewed

## Risks - Example YP-48
TPL-SPM-T12 ¦ project2-me.com
Owner Budget Tracker and Risk Register (T12): Risk Register
Example: YP-48 owner-side risks at month 15. Illustrative.
| As at (date) | 2028-04-03 |  | Probability score: 1 = up to 10%, 2 = 11-30%, 3 = 31-50%, 4 = 51-70%, 5 = over 70%.
| Risks not closed |  |  | Impact score, the higher of cost and time. Cost (index): 1 under 0.1, 2 from 0.1, 3 from 0.3, 4 from 0.6, 5 from 1.2. Time: 1 under 1 week, 2 up to 2 weeks, 3 up to 4 weeks, 4 up to 8 weeks, 5 over 8 weeks.
| Review cycle | Monthly, and after any major change |  | Level: Low 1-6, Medium 7-12, High 13-19, Critical 20-25 (same bands as the site's Shipyard Risk Register Template).
| High or Critical, not closed |  |  | Set your own scales before the first review and keep them for the whole project. Not financial or legal advice.
Expected value in contingency
Expected value outside contingency (e.g. currency)
Largest single cost impact
Risk ID | Risk | Category | Cause / trigger | Probability % | P (1-5) | Cost impact if it occurs (index) | Time impact (weeks) | I (1-5) | Score P x I | Level | Expected value (P% x cost) | Covered by contingency? (Y/N) | Expected value in contingency | Risk owner (a person) | Response | Status | Last reviewed
R-01 | Superstructure behind plan moves launch and delivery | Schedule | Trigger: hull and superstructure joining forecast later than month 16, or second-shift output below plan for 3 weeks | 55 |  | 1 | 6 |  |  |  |  | Y |  | Owner's representative | Weekly critical path review with the Yard; crew hiring and delivery costs tied to the forecast date, not the baseline | Open | 2028-04-03
R-03 | Contract currency strengthens against the Owner's funding currency | Commercial | Trigger: rate moves 2% or more against the budget rate; each milestone within 3 months | 40 |  | 3.05 | 0 |  |  |  |  | N |  | Owner's finance office | Hedging decision for milestones 4 to 7 put to the Owner this month; outside contingency | Open | 2028-04-03
R-05 | GT margin used up before the design is complete | Design | Trigger: T7 margin below 2.0 GT (now 2.7) | 15 |  | 1.5 | 6 |  |  |  |  | Y |  | Owner's representative (naval architect reports) | Every change screened for GT; no enclosed volume added after month 15 without an offset | Open | 2028-04-03
R-02 | Owner decisions late (stone samples, AV/IT specification) | Owner | Trigger: a decision passes its needed-by date in the decision log | 50 |  | 0.4 | 3 |  |  |  |  | Y |  | Owner's representative | Decision papers with needed-by dates in each weekly report; captain on site (CD-01) | Open | 2028-04-03
R-06 | Paint acceptance dispute delays delivery | Quality | Trigger: paint hold point failed, or reference panel not signed by month 20 | 35 |  | 0.4 | 3 |  |  |  |  | Y |  | Owner's representative | Reference panel and measurement method agreed before fairing; independent paint inspector | Open | 2028-04-03
R-04 | Owner-side certification not ready at delivery | Regulatory | Trigger: registration, manning or crew certificates not planned by month 24 | 20 |  | 0.3 | 6 |  |  |  |  | Y |  | Build captain | Owner-side certification plan with dates in the master schedule; flag contacted early | Open | 2028-04-03
R-07 | Owner-furnished tender late or does not fit the garage | Procurement | Trigger: tender builder misses its factory test date; garage interface drawing not approved by month 16 | 20 |  | 0.4 | 6 |  |  |  |  | Y |  | Build captain | Interface drawing approved by the Yard and the tender builder; delivery date in the owner-supply annex | Open | 2028-04-03
R-08 | Noise and vibration limits missed at sea trials | Technical | Trigger: Yard's prediction report shows less than the agreed margin in any named space | 20 |  | 0.3 | 6 |  |  |  |  | Y |  | Owner's representative | Independent N&V consultant reviews predictions and mounts before installation | Open | 2028-04-03
R-09 | AV/IT allowance overrun grows further | Commercial | Trigger: final AV/IT specification priced above the Yard's budget quote | 40 |  | 0.25 | 0 |  |  |  |  | Y |  | Owner's representative | Specification priced in two options before the Owner signs it off | Open | 2028-04-03
R-10 | Refund guarantee or insurance expires before the forecast delivery | Contract | Trigger: forecast delivery within 3 months of the guarantee expiry date | 20 |  | 0.15 | 0 |  |  |  |  | Y |  | Project manager with counsel | Extension requested as soon as the trigger is hit; contract calendar reminder | Open | 2028-04-03
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Probabilities, impacts and owners are illustrative. R-03 (currency) is marked N: it is managed by a hedging decision, not by the contingency.