## Read Me
TPL-SPM-T13 ¦ project2-me.com
Yacht Procurement Matrix and Long-Lead Tracker (T13)
Superyacht Project Management ¦ Free PM Templates & Documents for Yacht and Shipyard Projects
From project2-me.com, lesson: The Yacht Procurement Map: Yard Scope, Owner-Furnished Equipment and the Makers List.
What is in this file
Blank: the procurement matrix, 60 empty rows, with all formulas and counters.
Example (YP-48, illustrative): the 13-line matrix from the lesson, as at the end of month 15.
How to use it
One row per package or item that someone has to buy: yard scope, yard scope under an allowance, and owner-furnished equipment (OFE).
White cells are inputs, grey cells are formulas. Enter the 'As at' date, the contract delivery date and the yacht warranty length first.
Planned installation start and schedule float come from the master schedule (early start and total float of the task that needs the item).
Lead time is order to arrival at the yard, from the maker's confirmed quotation or production slot. The receipt buffer covers unloading, receipt inspection and preservation.
Latest safe order date = planned installation + float - receipt buffer - lead time. Ordering on that date uses all the float.
Order float = latest safe order date minus the order date. While the order is not placed, the 'As at' date is used, so the figure shrinks every day. Negative = the installation will start later than the schedule allows.
Delivery margin compares the forecast or actual arrival with the latest date the item can arrive (installation + float - buffer).
Interface data: the date the Yard needs weights, dimensions, foundation loads, power and data connections from the supplier. For owner-furnished items this is often the Owner's first real deadline, long before the item itself is needed.
Cover vs yacht warranty compares the maker's warranty end with the end of the yacht warranty. Negative = the maker's cover ends first. For yard-scope items that gap is the Yard's to manage under the contract; for OFE it is the Owner's.
Status reads, in order: installed, at yard, no order needed, not ordered (overdue / due / not yet), on order (delivery threatens float / late vs plan / on order).
Counters at the top: orders overdue, due within the warning period, ordered after the latest safe date, deliveries eating float, interface data overdue or late, delivered items without their certificate, FAT open points, warranty gaps.
About the example
Illustrative project: Project YP-48 is fictional. Its parameters are chosen from publicly reported industry ranges so the numbers are realistic, but no real yard, owner or yacht is described.
Dates use the YP-48 master schedule calendar: contract 2027-01-04, 22 working days per month, delivery 2029-07-16. The example is shown as at 2028-04-10 (end of month 15).
Lead times are PLACEHOLDERS, not maker data. For the six long-lead lines they reproduce the order-to-delivery spans of the YP-48 master schedule; for the other items they were chosen only to make the logic readable. Replace every one.
Makers and suppliers are generic (Maker P1, Tender builder T1). Warranty terms in the example are illustrative.
Classification society (Lloyd's Register) and flag (Cayman Islands) are illustrative choices of the series; the certificate column does not quote class rules. Confirm certificate requirements with class and the flag for your project.
This file is a planning aid, not legal advice. The contract, the makers list, class and the flag decide.

## Blank
TPL-SPM-T13 ¦ project2-me.com
Yacht Procurement Matrix and Long-Lead Tracker
Yard scope, allowances and owner-furnished equipment on one sheet: makers list, latest safe order date, FAT, delivery, certificate, installation and warranty.
| As at (date) |  |  | Lines |  |  |  | Orders due soon |  |  |  | Interface data received late
| Contract delivery date |  |  | Owner-furnished (OFE) lines |  |  |  | Ordered after latest safe date |  |  |  | Delivered, certificate pending
| Yacht warranty (months) | 12 |  | Allowance lines |  |  |  | Deliveries eating float |  |  |  | FAT open points or fail
| Warn when order is due within (days) | 30 |  | Orders overdue |  |  |  | Interface data overdue |  |  |  | Maker warranty short of yacht warranty
Yacht warranty ends
White cells are inputs; blue-grey headers and grey cells are formulas. Latest safe order date = planned installation + float - receipt buffer - lead time. Order float uses the order date, or the 'As at' date while the order is not placed.
Lead times must come from the maker's confirmed quotation or production slot. In the example sheet they are placeholders.
No | Package / item | WBS / schedule activity | Scope owner | Makers list entry | "Or equal" allowed? | Supplier / maker (as ordered) | Class / flag certificate required | Warrants the item to the Owner | Interface data needed by | Interface data received | Planned installation start | Schedule float at installation (days) | Lead time, order to yard (days) | Receipt buffer (days) | Latest safe order date | Order placed (date or n/a) | Order float (days) | FAT date (planned or actual) | FAT result | Delivery to yard, forecast | Delivery to yard, actual | Delivery margin (days) | Class / flag certificate status | Installation started | Maker warranty start | Maker warranty (months) | Maker warranty ends | Cover vs yacht warranty (days) | Interface data | Status | Owner-side action / notes
Formulas:
Maker warranty ends = IF(OR([Maker warranty start]="",[Maker warranty (months)]=""),"",EDATE([Maker warranty start],[Maker warranty (months)]))

## Example (YP-48, illustrative)
TPL-SPM-T13 ¦ project2-me.com
Yacht Procurement Matrix and Long-Lead Tracker: YP-48 at month 15
Illustrative example. Project YP-48 is fictional; lead times are placeholders, makers are generic.
| As at (date) | 2028-04-10 |  | Lines |  |  |  | Orders due soon |  |  |  | Interface data received late
| Contract delivery date | 2029-07-16 |  | Owner-furnished (OFE) lines |  |  |  | Ordered after latest safe date |  |  |  | Delivered, certificate pending
| Yacht warranty (months) | 12 |  | Allowance lines |  |  |  | Deliveries eating float |  |  |  | FAT open points or fail
| Warn when order is due within (days) | 30 |  | Orders overdue |  |  |  | Interface data overdue |  |  |  | Maker warranty short of yacht warranty
Yacht warranty ends
White cells are inputs; blue-grey headers and grey cells are formulas. Latest safe order date = planned installation + float - receipt buffer - lead time. Order float uses the order date, or the 'As at' date while the order is not placed.
Lead times must come from the maker's confirmed quotation or production slot. In the example sheet they are placeholders.
No | Package / item | WBS / schedule activity | Scope owner | Makers list entry | "Or equal" allowed? | Supplier / maker (as ordered) | Class / flag certificate required | Warrants the item to the Owner | Interface data needed by | Interface data received | Planned installation start | Schedule float at installation (days) | Lead time, order to yard (days) | Receipt buffer (days) | Latest safe order date | Order placed (date or n/a) | Order float (days) | FAT date (planned or actual) | FAT result | Delivery to yard, forecast | Delivery to yard, actual | Delivery margin (days) | Class / flag certificate status | Installation started | Maker warranty start | Maker warranty (months) | Maker warranty ends | Cover vs yacht warranty (days) | Interface data | Status | Owner-side action / notes
1 | Propulsion package (main engines, gearboxes) | 3.1 / 5.1 | Yard | Two approved makers listed | No | Maker P1 (from the list) | Class unit certificate, class attends FAT | Yard (maker warranty passed through) | 2027-04-06 | 2027-03-31 | 2028-01-07 | 32 | 324 | 14 |  | 2027-02-03 |  | 2027-12-14 | Pass |  | 2027-12-21 |  | Received | 2028-01-07 | 2029-07-16 | 12 |  |  |  |  | Yard negotiated maker warranty to run from yacht delivery
2 | Generator sets | 3.2 / 5.3 | Yard | Two approved makers listed | Yes, Owner approves | Maker G2 (from the list) | Class unit certificate, class attends FAT | Yard (maker warranty passed through) | 2027-04-06 | 2027-04-06 | 2028-02-08 | 30 | 326 | 14 |  | 2027-03-05 |  | 2028-01-13 | Pass |  | 2028-01-20 |  | Received | 2028-02-08 | 2028-01-20 | 18 |  |  |  |  | Maker terms run from shipment: ask the Yard how the gap to the yacht warranty is covered
3 | Stabilizers (zero-speed function) | 3.3 / 5.3 | Yard | One maker, named at Owner's request | No | Maker S1 (Owner's choice) | Per class rules: confirm scope with class | Yard (maker warranty passed through) | 2027-04-06 | 2027-04-19 | 2028-02-08 | 30 | 326 | 14 |  | 2027-03-05 |  | 2028-01-13 | Pass with open points |  | 2028-01-24 |  | Pending | 2028-02-08 | [6 empty] | FAT open point: control software update. Maker certificate not in delivery documents
4 | Glazing and exterior doors | 3.4 / 6.2 | Yard | Specialist named, or equal | Yes, Owner approves | Glazing specialist W1 | Approved drawings and test reports | Yard | 2027-08-06 | 2027-08-06 | 2029-01-11 | 32 | 264 | 14 |  | 2027-08-06 |  | 2028-04-10 | Planned | 2028-04-25 |  |  | Pending | [7 empty] | Order revised for VO-02 (wheelhouse windows)
5 | Interior joinery package | 3.5 / 7.1 | Yard | Outfitter named in makers list | No | Interior outfitter J1 | Material certificates per specification | Yard | 2027-08-06 | 2027-08-06 | 2028-04-10 | 30 | 202 | 14 |  | 2027-08-06 |  |  | n/a | 2028-04-14 |  |  | Pending | [7 empty] | Prefabrication behind: two stone samples waited for the Owner
6 | Navigation package | 3.6 / 7.2 | Yard | Listed maker, or equal | Yes, Owner approves | Maker N2 (accepted equivalent) | Per flag and code: confirm with class as RO | Yard (maker warranty passed through) | 2028-01-07 | 2027-12-23 | 2028-09-11 | 30 | 172 | 14 |  | 2028-02-08 |  |  | n/a | 2028-08-25 |  |  | Pending | [7 empty] | Equivalent accepted in writing at month 9, logged as no-cost change
7 | AV/IT systems | 3.6 / 7.2 | Yard (allowance) | None: Owner's specification | n/a | AV/IT integrator (Yard subcontract) | n/a | Yard | 2028-03-09 | 2028-03-24 | 2028-09-11 | 30 | 172 | 14 |  | 2028-03-30 |  | 2028-08-10 | Planned | 2028-09-05 |  |  | n/a | [7 empty] | Order placed after the Owner signed off the specification: part of the float used
8 | Tender garage crane | 6.2 | Yard | Two approved makers listed | No |  | Per class rules: confirm scope with class | Yard | 2027-09-07 | 2027-09-07 | 2029-01-11 | 32 | 243 | 14 | [16 empty] | Capacity to be re-checked for the larger limo tender (CR-06)
9 | Limo tender | 8.3 (needed for sea trials) | Owner (OFE) | Owner's own contract | n/a | Tender builder T1 | Maker's certificates; flag requirements to confirm | Maker direct to Owner | 2027-08-06 | 2028-03-09 | 2029-03-14 | 30 | 365 | 14 | [16 empty] | Larger tender chosen after signing; order waits for CR-06 decision
10 | RIB tender | 8.3 (needed for sea trials) | Owner (OFE) | Owner's own contract | n/a |  | Maker's certificates; flag requirements to confirm | Maker direct to Owner | 2027-08-06 | 2027-07-22 | 2029-03-14 | 30 | 182 | 14
11 | Loose furniture | 8.5 | Yard (allowance) | Design Studio selections | n/a |  | Material certificates per specification | Yard | 2028-09-11 |  | 2029-05-15 | 0 | 182 | 14 | [16 empty] | Selections needed by month 20; allowance spend tracked in the owner budget
12 | Water toys and dive equipment | 8.5 | Owner (OFE) | Owner's own purchase | n/a |  | n/a | Maker direct to Owner | 2028-09-11 |  | 2029-05-15 | 0 | 122 | 14 | [16 empty] | Stowage sizes to the Yard by month 20
13 | Art | 8.5 | Owner (OFE) | Owner's collection | n/a | Owner's art adviser | n/a | Owner's own insurance and handler | 2028-03-09 |  | 2029-06-14 | 0 |  | 14 |  | n/a | [14 empty] | Fixing points and weights needed for joinery backing: not received
Formulas:
Maker warranty ends = IF(OR([Maker warranty start]="",[Maker warranty (months)]=""),"",EDATE([Maker warranty start],[Maker warranty (months)]))