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Ship Repair Agreement: Sample Template
Editable sample agreement for a drydocking or repair job based on a repair specification, with unit rates, a work order procedure for additional work, options and drafting notes. Not legal advice.

	Important: sample template, not legal advice
This is a sample template published by project2-me.com for planning and training purposes. It is not legal advice and has not been prepared for any particular vessel, yard or jurisdiction.
Repair contracts decide who carries the risk of damage to a valuable ship in someone else’s custody. Have the final text reviewed by a qualified maritime lawyer before signature, and check its liability and insurance terms with the vessel’s hull and machinery and P&I insurers.
This template does not replace the published standard forms (such as BIMCO REPAIRCON) or a yard’s negotiated terms. It is written from scratch to show how the usual mechanisms fit together; it does not reproduce the wording, numbering or structure of any standard form.
No figure in this template is a recommendation. Every rate, percentage, period and amount is left blank for the parties to negotiate.



How to use this template
•	Fields in brackets and highlighted, such as [VESSEL NAME] or [NUMBER] hours, must be completed or deleted.
•	Where alternatives are offered as [Option A] / [Option B], keep one and delete the others.
•	Drafting notes, in grey italics, explain what to watch for. Delete all drafting notes and this cover page before the agreement is issued for signature.
•	Check every cross reference after clauses are added or removed; numbering is typed, not automatic.
•	Before using the template, work through the jurisdiction checklist that follows the contents with a lawyer qualified in the governing law.
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Before you use this template in your jurisdiction
This template is not written for any one country. The parties choose the governing law and the forum, and the rules of the place where the work is done still apply. The points below are where national law most often overrides, limits or adds to a contract term. Ask a lawyer qualified in the governing law, and in the law of the place of work if different, to check each point before the template is used.
Points for any contract
□	Governing law and forum. Is the chosen law and forum valid for these parties? If arbitration is chosen, can an award be enforced in the country where the other party has assets?
□	Mandatory local rules. Which rules of the place of work on employment, health and safety, environment, customs and permits apply whatever law the contract chooses?
□	Agreed damages. Can a court reduce or refuse delay damages or a penalty it finds excessive, and must the rate be a genuine estimate of loss?
□	Limits of liability. Which liabilities cannot be excluded or capped, for example for intent, gross negligence, death or personal injury, or breach of statutory duties?
□	Payment terms. Do local rules fix maximum payment periods, statutory interest on late payment, or limits on retention and on conditional payment clauses?
□	Guarantees and security. What form must a bank guarantee or other security take to be enforceable, and are there local banking or exchange control rules?
□	Tax. VAT or sales tax on the price, withholding tax on payments to foreign parties, and any stamp duty or registration charge on the signed contract.
□	Form and language. Must the contract be in the local language, signed by registered signatories, notarised or registered to be valid or enforceable?
□	Insurance. Which insurances are compulsory locally, and must they be placed with local insurers?
□	Sanctions and export controls. Do sanctions or export rules affect a party, the vessel, the equipment or the payment route?

Points for this type of contract
□	Right to retain the vessel. What lien or right of retention does the yard have under local law, and does it survive redelivery?
□	Customs status. How are the vessel, spares and owner’s supplies treated for customs while at the yard?
□	Waste and environment. Who must hold the permits for waste, sludge, blasting grit and hazardous materials removed from the vessel?

Delete this page, with the cover page and the drafting notes, before the contract is issued for signature.


SHIP REPAIR AGREEMENT
for repairs and drydocking of [VESSEL NAME], IMO number [IMO NUMBER]
This Agreement is made on [DATE] between:
(1)	[YARD COMPANY NAME], a company incorporated in [COUNTRY] with its registered office at [ADDRESS] (the “Yard”); and
(2)	[OWNER NAME], a company incorporated in [COUNTRY] with its registered office at [ADDRESS] (the “Owner”), [acting through its manager MANAGER NAME].
Background
(A)	The Owner has issued the Repair Specification and the Yard has submitted the Quotation.
(B)	The parties have agreed the terms on which the Yard will carry out the Works.
The parties agree as follows:
1.	Definitions and interpretation
1.1	In this Agreement the following words have the meanings given below:
(a)	“Additional Work” means work not included in the Repair Specification as accepted in the Quotation, including work arising from inspection findings, ordered under Clause 5.
(b)	“Agreement” means this ship repair agreement including its Schedules, as supplemented by Work Orders.
(c)	“Arrival Date” means the date stated in Clause 6.1.
(d)	“Contract Period” means the period stated in Clause 6.4, as adjusted under this Agreement.
(e)	“Contract Price” means the price for the Works calculated under Clause 4.
(f)	“Dock Days” means days, or parts of days, during which the Vessel occupies the dry dock, from [the dock being pumped dry / the Vessel entering the dock] until [the Vessel leaves the dock / the dock gate is opened].
(g)	“Docking Schedule” means the schedule in Schedule C, as updated under this Agreement.
(h)	“General Services” means the services listed as such in the Quotation and Schedule B, such as docking and undocking, dockage, berthage, shore power, cooling water, fire line, cranage, garbage removal, gangway and fire watch.
(i)	“Owner’s Representative” means the superintendent appointed under Clause 9.
(j)	“Owner’s Supplies” means the materials, spare parts and equipment supplied by or for the Owner.
(k)	“Quotation” means the Yard’s quotation No. [NUMBER] dated [DATE], as accepted by the Owner.
(l)	“Redelivery” means the event described in Clause 12.3.
(m)	“Repair Specification” means the Owner’s repair specification in Schedule A.
(n)	“Unit Rate Schedule” means the rates and prices in Schedule B.
(o)	“Vessel” means the vessel described in Clause 2.
(p)	“Work Order” means a written order for Additional Work, or a written reduction of the Works, signed under Clause 5.
(q)	“Works” means the work described in the Repair Specification and accepted in the Quotation, together with all Additional Work and less any work deleted, under this Agreement.
(r)	“Working Day” means a day other than [DAYS OF REST AND PUBLIC HOLIDAYS AT THE YARD].
1.2	Headings are for convenience only. “Including” means including without limitation. “Days” means calendar days unless Working Days are stated. Times are local time at the Yard.
2.	Parties, Vessel and Works
2.1	The Vessel is:
	Name / IMO number
	[VESSEL NAME] / [IMO NUMBER]

	Type / flag / port of registry
	[TYPE] / [FLAG] / [PORT]

	Classification society / class notation
	[CLASSIFICATION SOCIETY] / [NOTATION]

	Length overall / breadth / lightship
	[METRES] / [METRES] / [TONNES]

	Arrival draught and trim (expected)
	[DRAUGHT FORWARD / AFT]

	Docking plan
	Drawing No. [NUMBER], revision [REV], provided under Clause 6.2



2.2	The Yard shall carry out the Works at its facility at [YARD NAME AND LOCATION] in a good and workmanlike manner, with competent personnel, using new materials of the quality stated in the Repair Specification and approved by the classification society where class requirements apply.
2.3	The Yard may subcontract parts of the Works but remains responsible for them. Subcontracting of [MAJOR ITEMS, FOR EXAMPLE PROPELLER, SHAFT OR ENGINE OVERHAUL] needs the Owner’s prior consent.
3.	Contract documents and order of precedence
3.1	If the documents forming this Agreement are inconsistent, they take priority in the following order: this document, Work Orders (a later Work Order before an earlier one), the Repair Specification, the Quotation, and the other Schedules.
3.2	The Yard’s general terms and conditions, including any printed on the Quotation, do not apply [except SPECIFIED PROVISIONS, IF ANY].
Drafting note: A quotation often refers to the yard’s own standard terms, which may contain wider liability exclusions than the agreement. State clearly which document governs.
4.	Contract Price
4.1	The Contract Price is the total of:
(a)	the fixed prices for the items of the Repair Specification quoted as fixed price, amounting to [CURRENCY] [AMOUNT];
(b)	for items quoted on estimated quantities, the actual quantities used, measured under Clause 4.2 and priced at the Unit Rate Schedule;
(c)	General Services under Clause 4.3;
(d)	Additional Work priced under Clause 5; and
(e)	any other amounts expressly payable under this Agreement,
less deleted work under Clause 5.6 and any liquidated damages under Clause 7.
4.2	Quantities for unit-rate items shall be measured jointly by the Yard and the Owner’s Representative and recorded on measurement sheets signed by both [daily / on completion of each item]. Unsigned quantities may be disputed under Clause 21.
Drafting note: For steel renewal, state whether the rate is per kilogram of new steel fitted, how the weight is established (drawings, scale tickets or calculation), and whether the rate varies by location or plate thickness. Growth in steel and coating quantities is where repair costs usually move most.
4.3	General Services shall be charged:
[Option A] as a lump sum of [CURRENCY] [AMOUNT] for the quoted Contract Period, with the daily rates in the Unit Rate Schedule for each day by which the Contract Period is extended for reasons other than the Yard’s own delay; or
[Option B] at the daily and unit rates in the Unit Rate Schedule for the actual period and quantities used.
Drafting note: When comparing yard quotations, apply the same growth allowance to each quote at that yard’s own rates. Equal lump sums can end far apart once extra work and extra days are priced. Under Option A the Yard carries the cost of its own overrun; under Option B every extra day adds to the bill.
4.4	The prices are based on [normal working hours / the shift pattern in the Docking Schedule]. Overtime is charged at the Unit Rate Schedule only when ordered in writing by the Owner’s Representative. Overtime worked to recover the Yard’s own delay is at the Yard’s cost.
4.5	The rates in the Unit Rate Schedule apply to all Additional Work ordered during the Vessel’s stay, unless a Work Order states a different price.
4.6	Prices are in [CURRENCY] and are [exclusive / inclusive] of value added tax and similar taxes.
5.	Work Orders and Additional Work
5.1	The Yard shall carry out Additional Work only against a Work Order in the form of Schedule E, signed by the Owner’s Representative and the Yard’s project manager. The Owner’s Representative may sign Work Orders up to [CURRENCY] [AMOUNT] each; above that, the Owner’s [TITLE OR OFFICE] must sign.
5.2	Each Work Order shall state the work, the price basis (fixed price, Unit Rate Schedule or estimate) and the effect on the Contract Period and on the Dock Days.
5.3	For items of the Repair Specification described as “open, inspect and report” or similar, the Yard shall report its findings, with a proposal, price and time effect, within [NUMBER] hours after the inspection. The Owner shall decide within [NUMBER] hours after the report. Delay in the Owner’s decision beyond that period extends the Contract Period to the extent it delays Redelivery.
5.4	In an emergency, or where work must proceed immediately to avoid delay, the Owner’s Representative may instruct Additional Work orally. The instruction shall be confirmed by a Work Order within [NUMBER] hours. Except in such a case, the Yard is not entitled to payment for work done without a Work Order.
5.5	If the parties cannot agree the price or time effect of Additional Work, the Yard shall carry it out on the Owner’s written instruction. The price shall be based on the Unit Rate Schedule where it applies, and otherwise on a reasonable price, and any disagreement shall be decided under Clause 21.
5.6	The Owner may delete or reduce work by Work Order. The Contract Price shall be reduced by the quoted price of the deleted work, less the Yard’s costs already incurred, and the Contract Period adjusted accordingly.
5.7	The Yard shall keep a register of Work Orders showing their status, price and time effect, and present it at each daily meeting under Clause 9.3.
Drafting note: Variations are constant in repair work, so the approval route must be fast. Give each Work Order a time effect read from the docking schedule network before it is signed: insert and link the activity, then check the new undocking and Redelivery dates. That record decides later how many days of delay, if any, were the Yard’s.
6.	Arrival, docking and Contract Period
6.1	The Owner shall bring the Vessel to the Yard [on DATE / within the window from DATE to DATE] (the “Arrival Date”), and shall give the Yard notice of the expected time of arrival [NUMBER] days and [NUMBER] hours in advance.
6.2	The Owner shall provide the docking plan and the latest information on the Vessel’s condition, tanks and weights at least [NUMBER] days before arrival. The Yard is responsible for preparing the dock and the block arrangement in accordance with the docking plan.
6.3	The Yard shall dock the Vessel within [NUMBER] hours after her arrival, subject to weather and tide.
6.4	The Contract Period is [NUMBER] days, of which [NUMBER] are Dock Days. It starts [on arrival / on the first Working Day after arrival / when the Vessel is docked] and ends on Redelivery.
6.5	The Contract Period and the Dock Days are extended or reduced by:
(a)	the time effect of Work Orders, as stated in them or decided under Clause 21;
(b)	delay caused by the Owner, the Owner’s Representative, the crew, the Owner’s contractors or late or defective Owner’s Supplies, including late decisions under Clause 5.3;
(c)	events of force majeure under Clause 18.1; and
(d)	delay caused by the classification society or flag surveyors that is not the Yard’s fault.
6.6	The Yard shall notify the Owner’s Representative in writing within [NUMBER] hours after an event that it considers entitles it to an extension, with its expected effect, and record it in the daily delay log. [Option A] An event not notified in time gives no extension. [Option B] Late notice reduces the extension to the extent the Owner was prejudiced.
6.7	If the Vessel arrives later than [NUMBER] days after the Arrival Date (or the end of the arrival window):
[Option A] the Yard may cancel this Agreement by notice without liability to either party; or
[Option B] the Yard shall dock the Vessel at the first available opportunity and the Docking Schedule shall be adjusted, and the Owner shall pay the Yard’s documented costs caused by the late arrival.
6.8	If the Yard cannot dock the Vessel within [NUMBER] days after her timely arrival, the Owner may cancel this Agreement by notice, and the Yard shall [pay the Owner’s documented costs of the deviation up to AMOUNT / have no liability].
Drafting note: A docking is a short project with an unforgiving clock: the ship earns nothing on the blocks and the next vessel may be waiting for the dock. Agree how the arrival window and the dock slot interact, and what happens on either side if one of them is missed.
7.	Delay and early completion
7.1	If Redelivery takes place after the end of the Contract Period as adjusted under Clause 6:
[Option A] the Yard shall pay liquidated damages of [CURRENCY] [AMOUNT] for each day of delay after a grace period of [NUMBER] days, up to a maximum of [CURRENCY] [AMOUNT / PERCENTAGE OF THE CONTRACT PRICE];
[Option B] Option A applies and, in addition, the Owner shall pay the Yard a bonus of [CURRENCY] [AMOUNT] for each full day by which Redelivery precedes the end of the adjusted Contract Period, up to [CURRENCY] [AMOUNT]; or
[Option C] no liquidated damages apply, and the Owner’s claim for delay is subject to Clause 14.
7.2	Liquidated damages are deducted from the Contract Price. Where liquidated damages apply, they are the Owner’s only monetary remedy for late Redelivery.
Drafting note: The daily rate is usually set with the Vessel’s daily earnings or charter commitments in mind. Because the Contract Period moves with every Work Order and extension, the number of delay days depends on the time-impact records kept during the job; agree the method at the start. In some jurisdictions a rate out of proportion to any legitimate interest may not be enforceable.
8.	Owner’s Supplies and Owner’s contractors
8.1	The Owner shall deliver the Owner’s Supplies to the Yard by the dates in the Docking Schedule, clearly marked with the Vessel’s name and the Repair Specification item, with their documents and certificates.
8.2	The Yard shall receive the Owner’s Supplies, check them for quantity and visible damage, report discrepancies within [NUMBER] hours, store them safely and install them in accordance with the makers’ instructions. Handling is charged at [PERCENTAGE OF VALUE / THE UNIT RATE SCHEDULE].
8.3	The Yard is not responsible for the quality, design or performance of the Owner’s Supplies, but is responsible for its own installation work. Delay caused by late or defective Owner’s Supplies extends the Contract Period, and the Yard’s reasonable additional costs are payable by the Owner.
8.4	The Owner may engage its own contractors, including makers’ service engineers, to work on board. They shall follow the Yard’s safety rules and permit system and coordinate their work through the Yard’s project manager. The Owner is responsible for its contractors, and the Yard shall provide them with services at the Unit Rate Schedule.
8.5	Owner’s Supplies not used shall be returned to the Vessel or stored at the Owner’s request and cost.
Drafting note: Make clear which party coordinates owner’s contractors working in the same spaces as the Yard, and who is responsible for damage caused at the interface. Owner’s supervision of tests and commissioning can also shift responsibility for resulting damage, so define the roles in writing.
9.	Owner’s Representative, crew and daily meetings
9.1	The Owner shall appoint an Owner’s Representative and notify the Yard of the name and authority limits. The Yard shall appoint a project manager with authority to act for the Yard on all matters under this Agreement.
9.2	The Owner’s Representative may inspect the Works, witness tests and reject work that does not comply with this Agreement, giving reasons in writing. Inspection or approval by the Owner’s Representative does not relieve the Yard of its obligations.
9.3	The Owner’s Representative and the Yard’s project manager shall meet daily at [TIME] to review progress against the Docking Schedule, inspection findings, open Work Orders, delays and the forecast undocking and Redelivery dates. Minutes shall be signed by both.
9.4	The Owner may keep up to [NUMBER] crew members on board during the Works. Accommodation, meals and services for the crew are [provided by the Owner / charged at the Unit Rate Schedule]. The crew shall follow the Yard’s safety rules and shall not carry out work that interferes with the Works without the Yard’s consent.
Drafting note: Update the docking schedule at each daily meeting against a fixed status date, asking for the remaining duration of each open in-dock activity rather than only a percentage. Keep a weather log beside the coating activities; a humidity stop not recorded on the day is hard to prove later.
10.	Class, flag and statutory surveys
10.1	The Owner shall arrange the classification and flag surveys required for the Vessel and pay the surveyors’ fees [, except surveys needed only because of defects in the Yard’s work, which are for the Yard’s account].
10.2	The Yard shall give surveyors access to the Vessel and the work, and provide staging, lighting, ventilation, cleaning and gas-free conditions as needed for each survey.
10.3	Survey hold points, such as the bottom survey, tailshaft survey and final inspection before flooding the dock, shall be shown in the Docking Schedule and booked in advance with the surveyors.
10.4	Where class requirements apply, the Works shall be completed to the satisfaction of the classification society. Recommendations or conditions issued because of the Yard’s work shall be rectified by the Yard at its own cost before Redelivery.
11.	Safety, gas-freeing and environment
11.1	The Owner shall deliver the Vessel with the tanks and spaces listed in the Repair Specification cleaned and gas-free, or the Yard shall carry out cleaning and gas-freeing at the Unit Rate Schedule, as stated in the Repair Specification.
11.2	No hot work shall start in a space until it has been certified safe by [A MARINE CHEMIST / COMPETENT PERSON RECOGNISED AT THE YARD’S LOCATION]. The Yard shall maintain safe conditions during the Works.
11.3	The Yard’s safety rules and permit-to-work system apply to everyone working on the Vessel at the Yard, including the crew and the Owner’s contractors.
11.4	The Yard shall remove and dispose of sludge, oily water, garbage and other waste from the Works in accordance with the applicable law, and give the Owner receipts or certificates of disposal. Charges are at the Unit Rate Schedule.
11.5	If asbestos or other hazardous material not identified in the Repair Specification is found, the Yard shall stop the affected work and notify the Owner’s Representative. Its removal is Additional Work.
12.	Tests, sea trial and Redelivery
12.1	The Yard shall carry out the tests stated in the Repair Specification, witnessed by the Owner’s Representative and, where applicable, the surveyors, after giving [NUMBER] hours’ notice.
12.2	Sea trial:
[Option A] after undocking the Yard shall carry out a sea trial as stated in the Repair Specification. The Owner provides the master and crew, fuel and lubricants; the Yard provides its personnel. The Vessel remains under the command of her master during the trial; or
[Option B] no sea trial is included; any sea trial requested by the Owner is Additional Work.
12.3	When the Works have been completed and tested, apart from minor items agreed by the Owner’s Representative that do not affect the safe operation of the Vessel, and class items arising from the Works have been closed, the Yard shall tender the Vessel for redelivery. “Redelivery” takes place when both parties sign the redelivery protocol in the form of Schedule D.
12.4	Minor items outstanding at Redelivery shall be listed in the protocol with a completion date.
[Option A] The Owner may retain [AMOUNT] from the final payment until they are completed.
[Option B] No retention applies.
12.5	The Owner shall remove the Vessel from the Yard within [NUMBER] hours after Redelivery. After that, berthage and services are charged at the Unit Rate Schedule, and the Vessel remains at the Owner’s risk.
13.	Custody, risk and insurance
13.1	While the Vessel is at the Yard she remains the property of the Owner and is in the Yard’s care for the purpose of the Works. The Yard is responsible for loss of or damage to the Vessel and the Owner’s Supplies caused by the negligence or breach of the Yard or its subcontractors, subject to Clause 14.
13.2	The Owner shall keep the Vessel insured for hull and machinery and protection and indemnity risks while she is at the Yard, and shall inform its insurers of the yard stay and of the terms of this Agreement.
13.3	The Yard shall maintain ship repairer’s liability insurance with a limit of not less than [CURRENCY] [AMOUNT] per event, together with employer’s liability and other insurance required by law, and shall provide certificates on request.
13.4	Waiver of subrogation:
[Option A] the Owner shall procure that its hull and machinery insurers waive subrogation against the Yard for losses above the Yard’s limit of liability in Clause 14; or
[Option B] no waiver of subrogation is given.
Drafting note: Before accepting a liability limit or a waiver of recourse, check with the hull and machinery underwriters that the cover remains in place, and whether costs such as superintendent fees are covered. Some repair facilities also ask owners to give up their rights to limit liability; treat that as a separate negotiation point.
14.	Liability and limits
14.1	The Yard’s total liability for loss of or damage to the Vessel and the Owner’s property arising out of or in connection with this Agreement:
[Option A] shall not exceed [CURRENCY] [AMOUNT] for any one event and [CURRENCY] [AMOUNT] in total;
[Option B] shall not exceed [PERCENTAGE] percent of the Contract Price as finally adjusted; or
[Option C] is not subject to a cap, other than the exclusions in this Clause.
14.2	The Yard’s obligations under the guarantee in Clause 15 are [included in / outside] the limit above.
14.3	Neither party is liable for loss of hire, earnings, profit or use, demurrage or any other indirect or consequential loss, except the liquidated damages under Clause 7.
14.4	Nothing in this Agreement limits liability for death or personal injury caused by negligence, for fraud, for [gross negligence and] wilful misconduct, or for any other liability that cannot be limited under the governing law.
14.5	The Owner is responsible for damage to the Yard’s property caused by the Vessel, her crew or the Owner’s contractors, [subject to / without prejudice to] the Owner’s right to limit liability under the applicable law.
Drafting note: A cap expressed as a percentage of the Contract Price can be very small compared with the value of the Vessel. Set the limit with the realistic damage scenarios in mind (fire, dock flooding, damage during docking or undocking) and match it with the Yard’s insurance.
15.	Guarantee
15.1	The Yard guarantees the Works performed by it and the materials supplied by it against defects in workmanship and materials discovered within [NUMBER] months after Redelivery.
15.2	The Owner shall notify a defect in writing within [NUMBER] days after its discovery, and not later than [NUMBER] days after the guarantee period ends.
15.3	The Yard shall remedy the defect at its own facility. Where it is impractical to bring the Vessel to the Yard, the Owner may have the defect remedied elsewhere, and the Yard shall pay the reasonable cost, not exceeding what the same work would have cost at the Yard at the Unit Rate Schedule.
15.4	Coatings are guaranteed [as stated in the Repair Specification and the paint maker’s guarantee / for NUMBER months], provided surface preparation and application were carried out and recorded as specified.
15.5	The guarantee does not cover:
(a)	Owner’s Supplies and work carried out by the Owner’s contractors or the crew;
(b)	fair wear and tear, misuse, or damage caused after Redelivery by improper operation or maintenance;
(c)	defects in parts the Owner chose not to repair or renew after the Yard recommended it in writing; or
(d)	loss of hire, earnings or other consequential loss.
15.6	Where a maker’s or subcontractor’s guarantee is longer than the guarantee in this Clause, the Yard shall pass its benefit to the Owner.
16.	Payment
16.1	The Contract Price shall be paid:
[Option A] [PERCENTAGE] percent of the quoted price on arrival of the Vessel, and the balance within [NUMBER] days after receipt of the final invoice;
[Option B] in full within [NUMBER] days after receipt of the final invoice; or
[Option C] in instalments as follows: [SCHEDULE].
16.2	The Yard shall issue its final invoice within [NUMBER] days after Redelivery, with the list of Work Orders, signed measurement sheets and records of General Services.
16.3	The Owner shall pay the undisputed part of each invoice when due and shall state in writing, within [NUMBER] days after receipt, the items it disputes and why. Disputed items are settled under Clause 21.
16.4	Overdue amounts carry interest at [PERCENTAGE] percent per annum from the due date until payment.
16.5	Payments shall be made to [BANK, ACCOUNT DETAILS] in [CURRENCY], without set-off except for liquidated damages and amounts agreed in writing.
17.	Retention of the Vessel and security
17.1	To the extent permitted by the applicable law, the Yard may retain possession of the Vessel until the undisputed amounts due to it under this Agreement have been paid.
17.2	For amounts in dispute, the Yard shall release the Vessel against security in the form of [A BANK GUARANTEE / OTHER SECURITY ACCEPTABLE TO THE YARD, ACTING REASONABLY] for the disputed amount, plus [interest and costs / AMOUNT].
17.3	The Owner bears the costs of berthage and services during a justified retention under this Clause.
Drafting note: Whether a repairer has a right to keep the vessel until paid, and how it ranks against a mortgagee or other creditors, depends on the law of the place where the vessel lies and usually on the yard keeping possession. Do not assume this clause works the same way everywhere; take local advice for the Yard’s location.
18.	Force majeure, suspension and termination
18.1	“Force majeure” means an event beyond the reasonable control of the affected party, which it could not reasonably have avoided or overcome, such as natural disaster, fire not caused by the affected party, flood, war, epidemic declared by a public authority, acts of government, or strikes not limited to the affected party’s workforce. The affected party shall notify the other within [NUMBER] hours, and the Contract Period is extended by the resulting delay.
18.2	If force majeure prevents performance for more than [NUMBER] consecutive days, either party may terminate this Agreement by notice. The Owner shall pay for the work properly done up to termination and the Yard’s reasonable costs of making the Vessel ready to leave.
18.3	If the Owner fails to pay an undisputed amount within [NUMBER] days after written notice, the Yard may suspend the Works, and the Contract Period is extended by the period of suspension.
18.4	If the Yard fails to proceed with the Works with due diligence and does not remedy the failure within [NUMBER] days after written notice, or becomes insolvent, the Owner may terminate this Agreement by notice and remove the Vessel. The Owner shall pay for the work properly done, less its reasonable additional costs of completing the Works elsewhere [, up to AMOUNT].
18.5	On any termination the Yard shall undock the Vessel and make her ready to leave without delay, subject to Clause 17.
19.	Taxes and customs
19.1	The Yard bears taxes and duties on its own business, income and personnel. Value added tax and similar taxes on the Contract Price are [included / added to the invoice where applicable].
19.2	Owner’s Supplies shall be [imported under a temporary admission or ship’s spares procedure arranged by PARTY / cleared by the Owner]. Duties and charges on the Owner’s Supplies are for the Owner’s account.
Drafting note: Ship repair services and ship’s spares are often treated under special tax and customs rules. Confirm the treatment at the Yard’s location before agreeing this Clause.
20.	Confidentiality, assignment and notices
20.1	Each party shall keep the terms of this Agreement and information received from the other confidential, except for disclosure to insurers, classification society, flag State, financiers, professional advisers, or as required by law.
20.2	Neither party may assign this Agreement without the other’s written consent, except that the Owner may assign its rights to its financiers or the manager of the Vessel by notice.
20.3	Notices shall be in writing and in English, sent by hand, courier or email to the addresses below, and are effective on receipt. Day-to-day instructions on site may be given through the Owner’s Representative and the Yard’s project manager.
	Yard
	[NAME, ADDRESS, EMAIL, ATTENTION]

	Owner
	[NAME, ADDRESS, EMAIL, ATTENTION]

	Owner’s manager (if any)
	[NAME, ADDRESS, EMAIL, ATTENTION]



21.	Governing law and disputes
21.1	This Agreement and any non-contractual obligations arising out of it are governed by [Option A] English law / [Option B] the law of [JURISDICTION].
21.2	A dispute about measured quantities, workmanship or compliance with the Repair Specification may be referred by either party to an independent surveyor or expert appointed [BY AGREEMENT / BY APPOINTING BODY]. The expert’s decision is [final and binding / binding unless revised in arbitration].
21.3	Any other dispute shall be finally resolved by arbitration:
[Option A] in London under the terms of the London Maritime Arbitrators Association current at the start of the arbitration, including any small claims procedure for claims below [CURRENCY] [AMOUNT];
[Option B] in Singapore under the rules of the Singapore Chamber of Maritime Arbitration current at the start of the arbitration; or
[Option C] in [SEAT] under [ARBITRATION RULES] / by the courts of [JURISDICTION].
21.4	Pending resolution, the Yard shall continue the Works unless this Agreement has been terminated.
Drafting note: Repair disputes are often small relative to the cost of arbitration. A fast expert route for quantities and quality, and a small claims procedure where the chosen rules offer one, keep costs in proportion.
22.	General provisions
22.1	This Agreement is the entire agreement between the parties about the Works. Amendments are valid only in writing and signed by both parties; Work Orders signed under Clause 5 are valid amendments of the Works.
22.2	If any provision is invalid, the rest of this Agreement remains in force. A failure or delay in exercising a right is not a waiver of it. This Agreement may be signed in counterparts.
Signatures
The parties have signed this Agreement on the date stated at the beginning.
	Signed for and on behalf of the Yard, [YARD COMPANY NAME]
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]
	Signed for and on behalf of the Owner, [OWNER NAME]
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]





Schedule A: Repair Specification
Attach the Owner’s repair specification: [TITLE], revision [REVISION], dated [DATE], [NUMBER] items.
Recommended item layout
	Item No.
	Description and location
	Qty
	Unit
	Price basis
	Class item (Y/N)
	Dock work (Y/N)

	[1.01]
	[GENERAL SERVICES: DOCKING, UNDOCKING, DOCKAGE PER DAY]
	[QTY]
	[UNIT]
	[FIXED / UNIT RATE]
	[Y/N]
	[Y/N]

	[2.01]
	[HULL: HIGH-PRESSURE WASH, AREA]
	[QTY]
	[M2]
	[UNIT RATE]
	[Y/N]
	[Y]

	[3.01]
	[PROPELLER AND SHAFT: WITHDRAW TAILSHAFT FOR SURVEY]
	[QTY]
	[EACH]
	[FIXED]
	[Y]
	[Y]

	[4.01]
	[TANKS: OPEN, CLEAN, INSPECT AND REPORT, TANK NAME]
	[QTY]
	[EACH]
	[FIXED]
	[Y/N]
	[N]

	[5.01]
	[STEEL: RENEWAL AS FOUND, ESTIMATE]
	[QTY]
	[KG]
	[UNIT RATE]
	[Y]
	[Y/N]



The Repair Specification should state
•	Each item with location, quantity, unit and acceptance criteria, organised so that it can be priced and scheduled.
•	Which items need a dry hull (and therefore use Dock Days) and which can be done afloat or in the shop.
•	“Open, inspect and report” items, with the decision that follows each inspection.
•	Owner’s Supplies, with delivery dates and the items they belong to.
•	Tanks and spaces to be delivered gas-free, and by whom.
•	Tests, surveys and the sea trial, if any.


Schedule B: Unit Rate Schedule
All rates in [CURRENCY], [exclusive / inclusive] of value added tax. Rates apply to quoted estimated quantities and to Additional Work.
General Services
	Service
	Unit
	Rate

	Docking and undocking
	per operation
	[AMOUNT]

	Dockage
	per day or part day
	[AMOUNT]

	Berthage afloat
	per day
	[AMOUNT]

	Shore power connection / consumption
	per connection / per kWh
	[AMOUNT] / [AMOUNT]

	Cooling water, fire line
	per day
	[AMOUNT]

	Crane service
	per hour, by capacity
	[AMOUNT]

	Gangway, fire watch, security
	per day
	[AMOUNT]

	Garbage and waste removal
	per [M3 / SKIP / TONNE]
	[AMOUNT]

	Gas-free inspection and certificate
	per visit
	[AMOUNT]



Labour
	Trade
	Normal hours
	Overtime
	Sundays and holidays

	Steel worker / welder
	[AMOUNT] per hour
	[AMOUNT]
	[AMOUNT]

	Pipe fitter
	[AMOUNT] per hour
	[AMOUNT]
	[AMOUNT]

	Mechanic / fitter
	[AMOUNT] per hour
	[AMOUNT]
	[AMOUNT]

	Electrician
	[AMOUNT] per hour
	[AMOUNT]
	[AMOUNT]

	Painter / blaster
	[AMOUNT] per hour
	[AMOUNT]
	[AMOUNT]

	Staging
	[AMOUNT] per [M3 / M2]
	
	



Materials and unit-priced work
	Work
	Unit
	Rate
	Notes

	Steel renewal, shell and bottom
	per kg fitted
	[AMOUNT]
	[THICKNESS BAND, WEIGHT BASIS]

	Steel renewal, internal structure
	per kg fitted
	[AMOUNT]
	[LOCATION FACTOR, IF ANY]

	Pipe renewal
	per metre by diameter
	[AMOUNT]
	[MATERIAL]

	Hull blasting
	per m2, by grade
	[AMOUNT]
	[GRADE]

	Paint application
	per m2 per coat
	[AMOUNT]
	Paint [SUPPLIED BY YARD / OWNER]

	Material handling of Owner’s Supplies
	percent of value
	[PERCENTAGE]
	





Schedule C: Docking Schedule
Key dates
	Event
	Planned date / day
	Actual

	Arrival at the Yard
	[DATE]
	

	Docked and dock dry (Day 0)
	[DATE]
	

	Bottom survey with class
	Day [NUMBER]
	

	Tailshaft survey (if due)
	Day [NUMBER]
	

	Final class inspection before flooding
	Day [NUMBER]
	

	Undocking
	Day [NUMBER]
	

	Sea trial (if any)
	Day [NUMBER]
	

	Redelivery
	Day [NUMBER]
	



Working pattern and plan
	Shift pattern in dock
	[NUMBER] shifts of [NUMBER] hours, [NUMBER] days per week

	Shift pattern afloat
	[PATTERN]

	Owner’s Supplies required by
	[DATES BY ITEM]

	Critical in-dock chains (as planned)
	[FOR EXAMPLE PROPELLER AND SHAFT; HULL COATING; STEEL RENEWAL]

	Schedule file
	Attach the agreed bar chart or network, file [NAME], dated [DATE]



Drafting note: Only work that needs a dry hull consumes Dock Days. Plan everything else afloat or in the shop, and show the class hold points as linked activities with booked dates.


Schedule D: Redelivery Protocol
REDELIVERY PROTOCOL
	Vessel
	[VESSEL NAME], IMO number [NUMBER]

	Agreement
	Ship Repair Agreement dated [DATE] between [YARD COMPANY NAME] and [OWNER NAME]

	Place, date and time of Redelivery
	[PLACE], [DATE], [TIME] (local time)

	Statement
	The Yard redelivers and the Owner accepts the Vessel on completion of the Works, subject to the items listed below.

	Dock Days used / Contract Period used
	[NUMBER] / [NUMBER] days

	Work Orders issued
	Nos. [FROM] to [TO], as per the attached register

	Class and flag items
	[CLOSED / LIST OPEN ITEMS]

	Outstanding minor items
	[LIST, WITH COMPLETION DATES]

	Retention (if any)
	[AMOUNT]

	Start of guarantee period
	[DATE]

	Reservations
	[NONE / DESCRIBE]



	Signed for and on behalf of the Yard, [YARD COMPANY NAME]
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]
	Signed for and on behalf of the Owner, [OWNER NAME]
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]





Schedule E: Work Order form
	Work Order No. / date
	[NUMBER] / [DATE]

	Vessel / Agreement
	[VESSEL NAME] / Ship Repair Agreement dated [DATE]

	Type
	[ADDITIONAL WORK / DELETION / INSPECTION FINDING ON ITEM NUMBER]

	Description and location of the work
	[DESCRIPTION]

	Reason
	[FINDING / OWNER’S REQUEST / CLASS REQUIREMENT]

	Price basis
	[FIXED PRICE: AMOUNT / UNIT RATE SCHEDULE: ITEM AND QUANTITY / ESTIMATE: AMOUNT]

	Effect on Contract Period
	[+ / - NUMBER] days; new Redelivery date [DATE]

	Effect on Dock Days
	[+ / - NUMBER] days; new undocking date [DATE]

	Class involvement
	[YES: SURVEYOR ATTENDANCE / NO]

	Status
	[AGREED / PRICE OR TIME DISPUTED, WORK TO PROCEED UNDER Clause 5.5]



	Signed for and on behalf of the Yard (project manager)
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]
	Signed for and on behalf of the Owner (Owner’s Representative)
Signature: ______________________________
Name: [FULL NAME]
Title: [POSITION]
Date: [DATE]
Place: [PLACE]
In the presence of (witness): ______________________
Witness name and address: [NAME, ADDRESS]
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