|  | TPL-COMM-01 |
| --- | --- |

Owner – Yard – Class Communication Matrix

Free PM Templates & Documents for Shipyard Newbuild Projects · Template communication protocol for a shipyard newbuild contract

| Project / Vessel Name | [ Enter vessel name / hull no. ] |
| --- | --- |
| Shipyard | [ Enter yard name ] |
| Owner | [ Enter owner / operator ] |
| Classification Society | [ e.g. DNV / ABS / LR / BV ] |
| Prepared By / Date | [ Name ] / [ Date ] |

This matrix defines who communicates what, to whom, how often and through which channel during the newbuild construction period. Adapt the representatives, frequencies and deadlines to your own contract and project communication plan. Rows involving the Classification Society only apply where a survey or certification action is required.

| Communication Item | Frequency | Yard Rep. | Owner Rep. | Class Rep. | Channel / Method | Key Deliverable | Deadline / Trigger |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Weekly Progress Meeting | Weekly | Project Manager | Owner's Site Rep. | — | In-person / video call | Minutes of Meeting (MoM) | Every Monday |
| Monthly Progress Report | Monthly | Project Manager | Owner's PM | — | Formal report (PDF) | Progress report + updated schedule | 5th working day of month |
| Design Review Meeting | Per design package | Design Manager | Owner's Technical Rep. | As required | In-person / video call | Approved drawing / review comments | Per design review schedule |
| Technical Query (TQ) / RFI | As required | Design Manager | Owner's Technical Rep. | — | Email / document control system | TQ response | Within 5 working days |
| Non-Conformance Report (NCR) Notification | As raised | QA/QC Manager | Owner's QA Rep. | Class Surveyor | NCR form via document control | NCR + corrective action plan | Within 24 hours of discovery |
| Hold Point / Witness Point Notification | Per ITP | Production Manager | Owner's Site Rep. | Class Surveyor | Written notice (email / system) | Inspection sign-off | Min. 48 hours advance notice |
| Class Survey Scheduling | Per ITP milestones | QA/QC Manager | Copied for information | Class Surveyor | Email / class society portal | Survey booking confirmation | 2 weeks in advance |
| Variation Order / Change Request | As required | Project Manager | Owner's PM | — | Formal change request form | Approved VO with cost / schedule impact | Per contract terms |
| Milestone Completion Certificate | At each milestone | Project Manager | Owner's Site Rep. | Class Surveyor (where applicable) | Signed certificate | Milestone certificate | Within 2 days of milestone |
| Safety / Incident Notification | Immediate, if incident | HSE Manager | Owner's Site Rep. | — | Phone + written report | Incident report | Immediate + 24h written follow-up |
| Material / Equipment Delivery Notice | Per delivery | Procurement | Owner's Site Rep. (for OFE) | — | Email / logistics system | Delivery note / packing list | 3 days in advance |
| Owner Site Visit / Inspection | As requested | Project Manager | Owner's Representative | — | Scheduled visit | Visit report | 1 week advance notice |
| Sea Trial Notification & Program | Before sea trials | Project Manager | Owner's Representative | Class Surveyor | Formal trial program document | Trial program + attendee list | 3 weeks in advance |
| Final Documentation Handover | At delivery | Project Manager | Owner's Representative | Class Surveyor | Document package (physical + digital) | As-built docs, manuals, certificates | Before delivery date |
| Dispute / Escalation Notice | As required | Project Mgr. / Yard Mgmt. | Owner's PM / Management | — | Formal written notice | Escalation letter | Per contract dispute clause |

This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.

Downloaded from https://project2-me.com/dokumanlar  ·  © Project2-me