## ITP
TPL-ITP-01
Inspection & Test Plan (ITP) Template
Free PM Templates & Documents for Shipyard Newbuild Projects · Sample hold/witness points for a newbuild vessel — align with your class & contract
Project / Vessel Name |  | [ Enter vessel name / hull no. ]
Shipyard |  | [ Enter yard name ]
Classification Society |  | [ e.g. DNV / ABS / LR / BV ]
Contract / Hull No. |  | [ Enter contract or hull number ]
Inspection levels — W = Witness (notified, may attend) · H = Hold (mandatory sign-off before work proceeds) · R = Review (documentation review only)
Item No. | Activity / Inspection Item | Reference Standard / Drawing | Acceptance Criteria | Yard | Owner | Class | Responsible | Records | Status
Steel & Hull Structure
1 | Raw material identification & mill certificates | Class Rules Pt.2 | MTC matches cast / heat number | R | R | H | QA/QC | Mill Test Cert. | Passed
2 | Plate / profile dimensional & visual inspection | Yard QA Procedure | No laminations; correct thickness | W | R | R | QA/QC | Inspection Report | Passed
3 | Welding procedure qualification (WPS / PQR) | Class Rules Pt.3 | Approved WPS for each joint type | H | R | H | Welding Eng. | WPS / PQR file | Passed
4 | Welder qualification records | Class Rules Pt.3 | Valid, in-date welder certificates | R | R | R | QA/QC | Welder cert. register | Passed
5 | Butt weld NDT (UT / RT) | Class NDT requirements | 100% of class-required joints, no rejectable indications | W | R | H | NDT Contractor | NDT report | Open
6 | Block dimensional control / fairing check | Yard drawing tolerances | Within tolerance per approved drawing | W | W | R | Production | Survey report | Open
7 | Tank tightness test (hydro / air + soap) | Class Rules Pt.3 | No leakage at test pressure, held for required duration | H | W | H | Production | Test record | Pending
8 | Hull structural completion survey | Class Rules | Structure complete per approved drawings | H | W | H | Production Mgr | Survey report | Pending
Piping Systems
9 | Piping material & spool traceability | Class Rules Pt.2 | Material certificate matches spool marking | R | R | R | Piping Foreman | Traceability log | Pending
10 | Piping hydrostatic / pneumatic test | Class Rules Pt.3 / P&ID | 1.5× design pressure, no leaks, held per procedure | H | W | H | Piping Foreman | Test record | Pending
11 | Pipe flushing & cleanliness check | Yard Procedure | Cleanliness class achieved per system | W | R | R | Piping Foreman | Flushing report | Pending
12 | Valve & fitting functional check | Manufacturer spec | Correct operation, no leakage at seat/gland | W | R | R | Piping Foreman | Checklist | Pending
Machinery & Propulsion
13 | Main engine foundation alignment | Maker's Installation Manual | Alignment within maker tolerance | H | W | W | Machinery Foreman | Alignment record | Pending
14 | Shaft line alignment (bore sighting / laser) | Class Rules Pt.4 | Within class alignment tolerance | H | W | H | Machinery Foreman | Alignment report | Pending
15 | Main engine installation & bolt torque check | Maker's Manual | Torque values per maker specification | W | R | R | Machinery Foreman | Torque log | Pending
16 | Dock trial – main engine running test | Class Rules / Owner Spec. | Stable operation at specified test loads | H | H | H | Test Engineer | Dock trial report | Pending
Electrical & Automation
17 | Cable routing & segregation check | Class Rules Pt.4 / Drawing | Segregation and fire-zone routing per drawing | W | R | R | Electrical Foreman | Inspection checklist | Pending
18 | Insulation resistance (megger) test | Class Rules Pt.4 | Above minimum MΩ threshold per class | W | R | R | Electrical Foreman | Megger test log | Pending
19 | Switchboard functional & protection test | Maker Spec / Class Rules | Correct trip settings, no fault on load test | H | W | H | Electrical Eng. | Test report | Pending
20 | Emergency power / blackout recovery test | Class Rules Pt.4 | Auto-start and load transfer within required time | H | H | H | Electrical Eng. | Test report | Pending
Painting & Coating
21 | Surface preparation (blast profile) inspection | Coating Spec. / SSPC-SP10 | Correct profile & cleanliness grade (Sa 2.5) | W | R | R | Coating Inspector | Inspection report | Pending
22 | Dry film thickness (DFT) measurement | Coating Specification | DFT within spec range, no holidays detected | W | W | R | Coating Inspector | DFT survey | Pending
23 | Coating system final visual inspection | Coating Specification | No defects; correct colour and gloss per scheme | W | W | R | Coating Inspector | Inspection report | Pending
Sea Trial & Delivery
24 | Speed & fuel consumption trial | Class Rules / Owner Spec. | Meets contractual speed / consumption guarantee | H | H | H | Master / Test Eng. | Sea trial report | Pending
25 | Maneuvering & crash-stop trial | IMO / Class Rules | Turning circle & stopping distance within spec | H | H | H | Master / Test Eng. | Sea trial report | Pending
26 | Anchor windlass & mooring winch test | Class Rules Pt.4 | Rated pull / holding load achieved | W | W | W | Deck Foreman | Test record | Pending
27 | Navigation & communication equipment test | SOLAS / Class Rules | All equipment functional and calibrated | W | W | R | Electrical Eng. | Test checklist | Pending
28 | Noise & vibration measurement | Owner Spec. / ISO 6954 | Within contractual comfort limits | W | W | R | Test Engineer | Measurement report | Pending
29 | Final class survey & certificate issue | Class Rules | All hold points closed, certificate issued | R | W | H | Class Surveyor | Class certificate | Pending
30 | Owner acceptance & handover | Contract / Protocol of Delivery | Punch list closed, documentation package complete | H | H | R | Project Mgr | Protocol of Delivery | Pending
This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.
Downloaded from https://project2-me.com/dokumanlar · © Project2-me