## Master Schedule
TPL-SCHED-01
Newbuild Master Schedule Template
Free PM Templates & Documents for Shipyard Newbuild Projects · Interactive schedule — edit Start Date, Duration or % Complete and the chart updates
Project / Vessel Name |  | [ Enter vessel name / hull no. ]
Shipyard |  | [ Enter yard name ]
Owner |  | [ Enter owner / operator ]
Contract Effective Date (editable — shifts the whole chart) |  | 2026-01-05
Class Society |  | [ e.g. DNV / ABS / LR / BV ]
Prepared By / Date |  | [ Name ] / [ Date ]
WBS | Task Name | Type | Duration (days) | Start Date | Finish Date | Predecessor | % Complete | Responsible | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W54 | W55 | W56 | W57 | W58 | W59 | W60 | W61 | W62 | W63 | W64
1. Engineering & Design
1.1 | Contract Effective Date | Milestone | 0 | 2026-01-05 |  | - | 100% | Project Team
1.2 | Basic Design Approval (Classification Society) | Task | 42 | 2026-01-05 |  | - | 100% | Design Mgr
1.3 | Key Equipment Technical Specifications Finalized | Task | 28 | 2026-01-19 |  | 1.2 | 100% | Design Mgr
1.4 | Production Design – Hull (Zones 1-4) | Task | 70 | 2026-02-02 |  | 1.2 | 60% | Hull Design Lead
1.5 | Production Design – Machinery & Piping | Task | 70 | 2026-02-16 |  | 1.3 | 40% | M&E Design Lead
1.6 | Yard Working Drawings Released for Steel | Task | 28 | 2026-03-30 |  | 1.4 | 20% | Design Mgr
2. Procurement & Material
2.1 | Main Engine & Propulsion Package – PO Placed | Task | 14 | 2026-01-19 |  | 1.3 | 100% | Procurement
2.2 | Main Engine Delivery to Yard | Task | 7 | 2026-08-31 |  | 2.1 | 0% | Procurement
2.3 | Steel Plate & Profile Order | Task | 14 | 2026-03-02 |  | 1.6 | 50% | Procurement
2.4 | Steel Plate Delivery (First Batch) | Task | 7 | 2026-04-13 |  | 2.3 | 0% | Procurement
2.5 | Generators & Electrical Package – PO Placed | Task | 14 | 2026-03-16 |  | 1.5 | 30% | Procurement
2.6 | Deck Machinery Package – PO Placed | Task | 14 | 2026-03-16 |  | 1.5 | 30% | Procurement
2.7 | Paint & Coating System Procurement | Task | 7 | 2026-04-27 |  | 1.6 | 0% | Procurement
3. Steel & Hull Construction
3.1 | Steel Cutting Start (First Plate) | Milestone | 0 | 2026-04-27 |  | 2.4 | 0% | Production Mgr
3.2 | Sub-block Fabrication – Zone 1 (Engine Room) | Task | 56 | 2026-04-27 |  | 3.1 | 0% | Hull Shop
3.3 | Sub-block Fabrication – Zone 2 (Cargo / Mid-body) | Task | 56 | 2026-05-11 |  | 3.1 | 0% | Hull Shop
3.4 | Sub-block Fabrication – Zone 3 (Forward) | Task | 42 | 2026-05-25 |  | 3.1 | 0% | Hull Shop
3.5 | Sub-block Fabrication – Zone 4 (Accommodation) | Task | 42 | 2026-06-08 |  | 3.1 | 0% | Hull Shop
3.6 | Block Assembly & Pre-erection Outfitting | Task | 70 | 2026-06-22 |  | 3.2,3.3 | 0% | Production Mgr
3.7 | Keel Laying | Milestone | 0 | 2026-07-20 |  | 3.6 | 0% | Production Mgr
3.8 | Hull Erection – Blocks 1 to 6 | Task | 98 | 2026-07-20 |  | 3.7 | 0% | Erection Foreman
3.9 | Hull Erection – Superstructure Blocks | Task | 42 | 2026-09-28 |  | 3.8 | 0% | Erection Foreman
3.10 | Hull Structural Completion / Watertight | Milestone | 0 | 2026-11-09 |  | 3.9 | 0% | Production Mgr
4. Outfitting
4.1 | Engine Room Outfitting & Foundations | Task | 70 | 2026-08-17 |  | 3.8 | 0% | Outfit Mgr
4.2 | Main Engine & Gearbox Installation | Task | 28 | 2026-09-14 |  | 2.2,4.1 | 0% | Outfit Mgr
4.3 | Piping Installation (Engine Room + Deck) | Task | 84 | 2026-08-31 |  | 4.1 | 0% | Piping Foreman
4.4 | Electrical Cable Pulling & Termination | Task | 84 | 2026-09-14 |  | 3.9 | 0% | Electrical Foreman
4.5 | HVAC Installation | Task | 56 | 2026-10-12 |  | 4.4 | 0% | Outfit Mgr
4.6 | Accommodation Outfitting (Cabins, Galley, Mess) | Task | 70 | 2026-10-26 |  | 3.9 | 0% | Outfit Mgr
4.7 | Deck Machinery Installation (Winches, Cranes) | Task | 42 | 2026-11-09 |  | 2.6 | 0% | Outfit Mgr
4.8 | Navigation & Communication Equipment Install | Task | 28 | 2026-12-21 |  | 4.4 | 0% | Electrical Foreman
5. Painting & Coating
5.1 | Blast & Primer Coating – Block Stage | Task | 140 | 2026-05-25 |  | 3.2 | 0% | Coating Foreman
5.2 | Final Coating – Underwater Hull | Task | 21 | 2026-12-07 |  | 3.10,2.7 | 0% | Coating Foreman
5.3 | Final Coating – Topsides & Superstructure | Task | 28 | 2026-12-21 |  | 3.10,2.7 | 0% | Coating Foreman
5.4 | Draft Marks & Hull Markings | Task | 7 | 2027-01-18 |  | 5.2 | 0% | Coating Foreman
6. Testing & Commissioning
6.1 | Tank Testing (Ballast, Fuel, Fresh Water) | Task | 21 | 2026-11-23 |  | 3.10 | 0% | Test Engineer
6.2 | Dock Trials – Main Engine | Task | 14 | 2027-01-04 |  | 4.2,4.3 | 0% | Test Engineer
6.3 | Machinery & System Commissioning | Task | 42 | 2027-01-04 |  | 4.4,4.5 | 0% | Test Engineer
6.4 | Safety Equipment & Fire System Function Test | Task | 14 | 2027-02-01 |  | 4.8 | 0% | Test Engineer
7. Launch & Sea Trials
7.1 | Launching | Milestone | 0 | 2026-11-23 |  | 3.10 | 0% | Production Mgr
7.2 | Quay Outfitting (Post-Launch) | Task | 70 | 2026-11-23 |  | 7.1 | 0% | Outfit Mgr
7.3 | Sea Trial Preparation & Class Survey | Task | 14 | 2027-02-15 |  | 6.2,6.3 | 0% | Test Engineer
7.4 | Sea Trials (Speed, Endurance, Maneuvering) | Task | 7 | 2027-03-01 |  | 7.3 | 0% | Master / Test Eng.
7.5 | Class Certificate of Sea Trials Issued | Milestone | 0 | 2027-03-08 |  | 7.4 | 0% | Class Surveyor
8. Delivery
8.1 | Owner's Punch List Closeout | Task | 21 | 2027-03-01 |  | 7.4 | 0% | Project Mgr
8.2 | Final Class & Flag Survey | Task | 7 | 2027-03-15 |  | 8.1 | 0% | Class Surveyor
8.3 | Delivery & Handover to Owner | Milestone | 0 | 2027-03-29 |  | 8.2 | 0% | Project Mgr
8.4 | Flag Registration Complete | Task | 7 | 2027-03-29 |  | 8.3 | 0% | Project Mgr
Legend: ◆ Milestone · Pale bar = planned duration (Start→Finish) · Solid bar = completed portion (from % Complete) · Live: edit Start Date, Duration or % Complete on any row and the chart updates automatically
This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.
Downloaded from https://project2-me.com/dokumanlar · © Project2-me