## Cost Breakdown
TPL-CBS-01
Newbuild Cost Breakdown Structure
Free PM Templates & Documents for Shipyard Newbuild Projects · Illustrative CBS & budget tracker for a mid-size newbuild vessel
Project / Vessel Name |  | [ Enter vessel name / hull no. ]
Shipyard |  | [ Enter yard name ]
Total Contract Value |  | USD 18,500,000 [ Enter your contract value ]
Reporting Date |  | [ Date ]
CBS Code | Cost Category | Budget (USD) | Committed (USD) | Actual to Date (USD) | Remaining (USD) | % Spent | Notes
1.0 | Hull Structure & Steel | 3700000 | 3750000 | 3680000 | 20000 | 99.46% | Steel tonnage close to estimate; one plate re-order
2.0 | Machinery & Propulsion | 4810000 | 4900000 | 3150000 | 1660000 | 65.49% | Main engine + gearbox POs placed, progress payments ongoing
3.0 | Outfitting (Deck / Accommodation / HVAC) | 3515000 | 3400000 | 1750000 | 1765000 | 49.79% | Accommodation outfitting starting this quarter
4.0 | Electrical & Automation | 1480000 | 1510000 | 890000 | 590000 | 60.14% | Switchboard package slightly over original estimate
5.0 | Painting & Coating | 740000 | 700000 | 260000 | 480000 | 35.14% | Coating system supplier confirmed, blast stage in progress
6.0 | Owner Furnished Equipment – Interface & Install | 740000 | 740000 | 90000 | 650000 | 12.16% | Installation labor only; equipment supplied by Owner
7.0 | Class & Certification | 370000 | 370000 | 240000 | 130000 | 64.86% | Class fees + periodic survey costs
8.0 | Project Management & Engineering | 1295000 | 1295000 | 980000 | 315000 | 75.68% | Basic + production design largely complete
9.0 | Yard Overheads & Facilities | 925000 | 925000 | 610000 | 315000 | 65.95% | Dock/crane time and yard services allocation
10.0 | Contingency & Risk Reserve | 925000 | 0 | 45000 | 880000 | 4.865% | Drawdown for one approved variation order
TOTAL
This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.
Downloaded from https://project2-me.com/dokumanlar · © Project2-me