## Dashboard & Summary
NEWBUILDING PROJECT - MANAGEMENT & COST CONTROL DASHBOARD
TOTAL TARGET BUDGET |  |  | TOTAL ACTUAL COST | TOTAL VARIANCE STATUS | AVERAGE PROGRESS
27100000 |  |  | 22980000 | 4120000 | 55.06%
Group | System / Main Group Description | Target Budget ($) | Actual Cost ($)
100 | GENERAL PROJECT EXPENSES & ENGINEERING | 1250000 | 1180000
200 | HULL STRUCTURE & STEEL WORKS | 11300000 | 11150000
300 | Main Engine Supply & Commissioning | 5200000 | 4600000
400 | Pipe Spool Supply (Carbon Steel, Stainless, CuNiFe) | 4200000 | 3230000
500 | Marine Power/Signal Cables & Main Switchboards | 1800000 | 1150000
600 | ACCOMMODATION OUTFITTING & HVAC SYSTEM | 1400000 | 850000
700 | COATING, OUTSIDE OUTFITTING, DOCKING & DELIVERY | 1950000 | 820000
| TOTAL SUMMARY | 27100000 | 22980000

## Detailed CBS
NEWBUILDING VESSSEL PROJECT - COST BREAKDOWN STRUCTURE (CBS)
CBS Code | Level | Description / System Specification | Cost Type | Target Budget ($) | Actual Cost ($) | Variance ($) | Progress (%) | Status | Remarks
100 | L1 | GENERAL PROJECT EXPENSES & ENGINEERING |  | 1250000 | 1180000 | 70000 | 93.75% | In Progress
101 | L2 | Basic & Detailed Engineering / Design Services | Service/Survey | 450000 | 460000 | -10000 | 100% | Completed
102 | L2 | Classification Society, Surveys & Flag State Fees | Service/Survey | 250000 | 210000 | 40000 | 85% | In Progress
103 | L2 | Shipyard Project Management & Planning Labor | Labor | 350000 | 310000 | 40000 | 90% | In Progress
104 | L2 | Builder's Risk Insurance & Financing Costs | Indirect Cost | 200000 | 200000 | 0 | 100% | Completed
200 | L1 | HULL STRUCTURE & STEEL WORKS |  | 11300000 | 11150000 | 150000 | 95% | Completed
201 | L2 | Class Approved Marine Steel Plates & Profiles Procurement | Material | 2800000 | 2950000 | -150000 | 100% | Completed
202 | L2 | Block Fabrication, Pre-Outfitting & Assembly Subcontract | Subcontractor | 1500000 | 1550000 | -50000 | 100% | Completed
203 | L2 | Welding Consumables, Industrial Gases & NDT Testing | Material | 300000 | 290000 | 10000 | 100% | Completed
204 | L2 | Aluminum Superstructure Fabrication (Material + Labor) | Subcontractor | 200000 | 160000 | 40000 | 100% | Completed
300 | L1 | PROPULSION SYSTEM & MACHINERY SPACE EQUIPMENT |  | 6500000 | 6200000 | 300000 | 75% | In Progress
301 | L2 | Main Engine Supply & Commissioning | Material | 5200000 | 4600000 | 600000 | 57.5% | In Progress
302 | L2 | Auxiliary Diesel Generator Sets (3 Units) | Material | 1200000 | 1150000 | 50000 | 80% | In Progress
303 | L2 | Propeller, Shaft Line, Coupling & Steering Gear Systems | Material | 1100000 | 1050000 | 50000 | 50% | In Progress
304 | L2 | Bow & Stern Thruster Systems | Material | 700000 | 550000 | 150000 | 40% | In Progress
400 | L1 | PIPING SYSTEMS & OUTFITTING ELEMENTS |  | 2200000 | 1850000 | 350000 | 60% | In Progress
401 | L2 | Pipe Spool Supply (Carbon Steel, Stainless, CuNiFe) | Material | 4200000 | 3230000 | 970000 | 43.75% | In Progress
402 | L2 | Valves, Pumps, Hydrophores & Strainer Groups | Material | 600000 | 550000 | 50000 | 70% | In Progress
403 | L2 | Pipe Prefabrication & Onboard Installation Subcontract | Subcontractor | 500000 | 380000 | 120000 | 40% | In Progress
404 | L2 | Ballast Water Management System (BWMS) Unit | Material | 300000 | 200000 | 100000 | 20% | In Progress
500 | L1 | ELECTRICAL, AUTOMATION & NAVIGATION SYSTEMS |  | 2800000 | 2100000 | 700000 | 45% | In Progress
501 | L2 | Marine Power/Signal Cables & Main Switchboards | Material | 1800000 | 1150000 | 650000 | 26.67% | In Progress
502 | L2 | Integrated Automation & Alarm Monitoring System (IAS/AMS) | Material | 600000 | 450000 | 150000 | 30% | In Progress
503 | L2 | Navigation, Radio & Bridge Console Equipment | Material | 500000 | 200000 | 300000 | 10% | Planned
504 | L2 | Electrical Installation, Cable Pulling & Terminations Subcontract | Subcontractor | 700000 | 500000 | 200000 | 40% | In Progress
600 | L1 | ACCOMMODATION OUTFITTING & HVAC SYSTEM |  | 1400000 | 850000 | 550000 | 35% | In Progress
601 | L2 | Insulation, Wall/Ceiling Panels & Fire-Rated Doors | Material | 500000 | 420000 | 80000 | 70% | In Progress
602 | L2 | Furniture, Wet Units & Galley/Pantry Equipment | Service/Survey | 400000 | 150000 | 250000 | 15% | In Progress
603 | L2 | Central HVAC Units, ChILLers & Ducting Network | Material | 500000 | 280000 | 220000 | 20% | In Progress
700 | L1 | COATING, OUTSIDE OUTFITTING, DOCKING & DELIVERY |  | 1950000 | 820000 | 1130000 | 33.75% | In Progress
701 | L2 | Blasting Grit & Class-Approved Marine Coatings/Paints | Material | 600000 | 450000 | 150000 | 75% | In Progress
702 | L2 | Painting Application & Surface Preparation Subcontract | Subcontractor | 450000 | 250000 | 200000 | 50% | In Progress
703 | L2 | Deck Machinery (Windlass, Mooring Winches, Cranes) | Material | 500000 | 120000 | 380000 | 10% | Planned
704 | L2 | Drydocking, Launching Operations & Sea Trials | Service/Survey | 400000 | 0 | 400000 | 0% | Planned
TOTAL |  | GRAND TOTAL (VESSEL CAPITAL COST) |  | 27100000 | 22980000 | 4120000 | 55.06%

## Settings
Cost Type
Material
Labor
Subcontractor
Indirect Cost
Service/Survey
Status
Planned
In Progress
Completed
Delayed