## EVM Tracker
TPL-EVM-01
EVM (Earned Value) Tracker Template
Free PM Templates & Documents for Shipyard Newbuild Projects · Interactive — edit Planned/Actual % and Actual Cost, everything else recalculates
Project / Vessel Name |  | [ Enter vessel name / hull no. ]
Shipyard |  | [ Enter yard name ]
Total Contract Value (BAC) |  | USD 18,500,000 [ Enter your contract value ]
Data Date |  | [ Enter status date ]
WBS | Work Package | BAC (USD) | Planned % Complete | Actual % Complete | PV (USD) | EV (USD) | AC (USD) | SV (USD) | CV (USD) | SPI | CPI | Status
1.0 | Engineering & Design | 1850000 | 100% | 100% |  |  | 1760000
2.0 | Procurement & Material | 2220000 | 90% | 85% |  |  | 2050000
3.0 | Steel & Hull Construction | 4625000 | 70% | 60% |  |  | 2960000
4.0 | Outfitting | 3700000 | 40% | 30% |  |  | 1250000
5.0 | Painting & Coating | 925000 | 35% | 25% |  |  | 260000
6.0 | Testing & Commissioning | 1110000 | 15% | 5% |  |  | 65000
7.0 | Launch & Sea Trials | 925000 | 5% | 0% |  |  | 0
8.0 | Delivery | 555000 | 0% | 0% |  |  | 0
9.0 | Class & Certification | 370000 | 60% | 55% |  |  | 210000
10.0 | Yard Overheads & Facilities | 925000 | 60% | 60% |  |  | 610000
11.0 | Project Management | 925000 | 65% | 65% |  |  | 690000
12.0 | Contingency Reserve | 370000 | 0% | 0% |  |  | 45000
TOTAL
Formulas: PV=BAC×Planned% EV=BAC×Actual% SV=EV−PV CV=EV−AC SPI=EV/PV CPI=EV/AC. SPI/CPI ≥1.00 = ahead/under budget, <1.00 = behind/over budget. Live: edit Planned %, Actual % or Actual Cost (AC) on any row and every formula recalculates.
This document is provided as a free template by project2-me.com for project-management reference purposes only. It does not constitute engineering, classification or legal advice. Adapt all bracketed fields, quantities and acceptance criteria to your own contract, classification society rules and shipyard procedures before use.
Downloaded from https://project2-me.com/dokumanlar · © Project2-me